## Test Log
Date / time | Case ID | Card | Owner | Build | Expected result | Actual result | Status | Defect ID | Evidence
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P1 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 940e082 / 9e18f30 | Pilot budget: p95 upload acknowledgement (pending -> synced, online) <= 5 s. | PC A: '1.33-2.09 s across 5 runs; manual 1.22 s'. PC B: '2.08-4.46 s across 6 runs; 24.06 s on live capture 6 (2026-10-10)'. Pilot verdict: 'Not met on one run. Met on the other 11, including the 2026-10-16 live retest (3.44 s). Limit L2'. | Fail | DEF-10 | docs/migration/05f-pilot.md §4, §5 finding 3, §7 L2; evidence: product code = 940e082
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P2 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 940e082 / 9e18f30 | Pilot budget: sustained acknowledged events per client >= 20 events/s. | PC A: '≈ 1.9/s (capture 5: 300 events in 157 s)'. PC B: 'backlog drain of 210 events in 4.1 s ≈ 51/s'. Pilot verdict: 'Not demonstrated. Sources are paced by design: CSV Fast emits one flow per 0.35 s, ≤ 2.9/s. Each capture stores at most 300 events. Limit L1'. | Fail | DEF-11 | docs/migration/05f-pilot.md §4, §5 finding 4, §7 L1; evidence: product code = 940e082
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P4 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 940e082 | Pilot budget: live capture packet drop <= 1%. | PC A: '0% (0 of 848; 0 of 2,810)'. PC B: '0% (0 of 119,100; 0 of 740)'. Pilot verdict: 'Met'. | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P5 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 9e18f30 | Pilot budget: AlgoGuard process CPU peak <= 50% of the machine. | PC A: '24.5% (2-s samples, Test C)'. PC B: '6.3% (2-s samples, capture 18)'. Pilot verdict: 'Met'. Not the plan 3.4 soak budget (<= 80% over 30 min). | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P6 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 9e18f30 | Pilot budget: AlgoGuard process RAM (working set) peak <= 1 GB. | PC A: '294 MB'. PC B: '108 MB'. Pilot verdict: 'Met'. PC A samples cover 07:58-08:43Z on 2026-10-08 (first 32 min of a 46-min CSV run); PC B's cover 60 s of capture 18. | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-08 to 2026-10-16 (pilot) | PRF-01.P7 | PRF-01 | Afel Anthonielle V. Quirao | pilot 4c9666c / 940e082 / 9e18f30 | Pilot budget: local state-folder growth per PC, whole pilot <= 50 MB. | PC A: '0.051 -> 8.846 MiB (8.162 MiB is the model)'. PC B: '9.12 MiB in total'. Pilot verdict: 'Met'. | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-16 (pilot) | PRF-01.P3 | PRF-01 | Afel Anthonielle V. Quirao | pilot 9e18f30 (PC B) | Pilot budget: average live event-to-verdict lag <= 20 s (measured from a flow's last packet, so it includes the 15 s idle timeout). | PC A: 'not recorded'. PC B: '13.1 s' (capture 19, 2026-10-16). Pilot verdict: 'Met on PC B; not recorded on PC A'. This is not the plan 3.4 budget (p95 <= 500 ms excluding timeouts), which TC-11 measures. | Pass |  | docs/migration/05f-pilot.md §2, §4; evidence: product code = 940e082
2026-10-16 (pilot; time not stated) | SYS-03.P1 | SYS-03 | Cel Hendrix N. San Miguel | pilot 4c9666c / 940e082 | Each node only sees its own data; no record crosses nodes (SYS-03 card). | Pilot record: 'The two node UUIDs differ and each persisted across every restart from 2026-10-08 to 2026-10-16, including the deliberate restart in Test E.' (PC A d535e2fd-8392-4876-a945-c8d9c5184049, PC B 265f767e-f540-4f71-bf36-c7364f99ba59). 'No row was written under the other client's node or owner. Analysts can read only their own node, and the Administrator can read both.' | Pass |  | docs/migration/05f-pilot.md §1 (Accounts and nodes) and §7 (accepted on the physical pilot); 2026-10-08 to 2026-10-16; Tests A-D on 4c9666c, 2026-10-15/16 work on 940e082
2026-10-16 (pilot; time not stated) | SYS-03.P2 | SYS-03 | Cel Hendrix N. San Miguel | pilot 940e082 | TC-06: analyst A requests node B's alerts through the Data API: no rows returned; no private data in errors. | Pilot hosted RLS check, read-only, each account under the authenticated role with its own JWT subject, 2026-10-16: 'cel.hendrix (Administrator) - both nodes: 467 on PC A and 1,527 on PC B'; 'celpca (PC A analyst) - PC A only (467); PC B's node row is not visible'; 'bryntpcb (PC B analyst) - PC B only'. UI: the Administrator's Alert History on PC A showed only PC A's alerts (ordinary pages default to the installation's own node; finding 6). | Pass |  | docs/migration/05f-pilot.md §3 'Administrator reads across nodes'; evidence: product code = 940e082
2026-10-16 17:32 (pilot) | SYS-03.P4 | SYS-03 | Cel Hendrix N. San Miguel | pilot 9e18f30 (PC B) = 940e082 + test-cycle files | Disconnect and reconnect: pending events kept and synced once (SYS-03 card). | Pilot Test E, 2026-10-16, PC B: capture 12 started online at 09:29:04Z, went offline ~2 s later; 'It classified 210 flows offline, all held as pending.' 'Restarting offline refused sign-in, as designed.' bryntpcb signed in at 09:32:39Z; 'All 210 records were acknowledged between 09:32:44.6Z and 09:32:48.7Z, the last 9.5 s after sign-in. The cloud holds 210 events with 210 distinct event UUIDs, 210 traffic rows, 210 predictions and 139 alerts, all under PC B's node and owner. No PC A record changed.' | Pass |  | docs/migration/05f-pilot.md §3 'Test E'; evidence: product code = 940e082
2026-10-16 17:32 (pilot) | PRF-01.P8 | PRF-01 | Afel Anthonielle V. Quirao | pilot 9e18f30 (PC B) | Pilot budget: outage recovery - all pending synced <= 2 min after reconnect; 0 lost; 0 duplicates. | PC B: '9.5 s after sign-in; 0 lost; 0 duplicates'. Pilot verdict: 'Met. Timed from sign-in, because uploads after a restart wait for an online sign-in by design'. | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-16 17:40 (pilot) | SYS-03.P3 | SYS-03 | Cel Hendrix N. San Miguel | pilot 9e18f30 (PC B) = 940e082 + test-cycle files | TC-07: administrator revokes analyst B; B's prediction and capture refused; Restore re-enables. | Pilot Test F, 2026-10-16: 'The Administrator revoked bryntpcb on PC B's node at 09:40:58Z and restored it at 09:45:21Z, then revoked and restored once more at 09:50:38Z and 09:50:42Z. While revoked, PC B was refused, and the cloud accepted no capture and no event from it. The exact wording on PC B was not recorded. After Restore, PC B still refused to monitor until Retry uploads was pressed on its Dashboard.' Five Starts during the block opened empty captures 13-17 (finding 5, Low, routed to 6C.1). 'After Retry uploads, capture 18 ran normally: 332 flows, 234 stored.' Prediction while revoked is not separately recorded. | Pass |  | docs/migration/05f-pilot.md §3 'Test F' and §5 finding 5; evidence: product code = 940e082
2026-10-16 17:40 (pilot) | PRF-01.P9 | PRF-01 | Afel Anthonielle V. Quirao | pilot 9e18f30 (PC B) | Pilot budget: revocation / restore - refused on the next action; works again after restore. | PC B: 'refused immediately; works after Retry uploads'. Pilot verdict: 'Met, with the Retry uploads step now in the runbook'. | Pass |  | docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-19 10:45 | ENV-01.3 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | pip install -r requirements-dev.txt succeeds. | Exit code 0. Every requirement was already satisfied; nothing changed. | Pass |  | test-results/env_20261019/pip-install-requirements-dev.log; evidence: product code = 940e082
2026-10-19 10:45 | ENV-01.4 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | pip install pytest-cov pip-audit bandit succeeds. | Exit code 0. Installed pytest-cov 7.1.0 and coverage 7.16.2; pip-audit 2.10.1 and bandit 1.9.4 were already installed. | Pass |  | test-results/env_20261019/pip-install-test-tools.log; evidence: product code = 940e082
2026-10-19 10:45 | ENV-01.7 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Bundled datasets present and row counts recorded; UNSW_NB15_training-set.csv has 82,332 rows. | datasets/algoguard_big.csv 5,000 rows (1,597 Normal / 3,403 Attack); algoguard_bigger.csv 10,000 (3,194 / 6,806); algoguard_biggest.csv 20,000 (6,388 / 13,612); research/dataset/raw/UNSW_NB15_training-set.csv 82,332 rows, 45 columns (37,000 Normal / 45,332 Attack). SHA-256 of each file recorded. | Pass |  | test-results/env_20261019/dataset_counts.json; evidence: product code = 940e082
2026-10-19 10:46 | ENV-01.8 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Independent evaluation set built from the UNSW-NB15 training set with every row seen in training removed; row counts recorded (plan 5.1). | 82,332 rows loaded; 29,089 removed because their 15 features match a row in datasets/*.csv; 53,243 kept (20,674 Attack / 32,569 Normal). Generic attacks fall from 18,871 to 802 rows after removal; 7,387 kept rows repeat the features of another kept row. | Pass |  | test-results/env_20261019/independent_set_counts.json (built with scripts/evaluate_model.py row_keys()); evidence: product code = 940e082
2026-10-19 10:51 | TC-16 | ENV-02 | Afel Anthonielle V. Quirao | dafe5e5 | Line coverage of services/ >= 80% (pytest --cov=services). | TOTAL 1,869 statements, 312 missed: 83% line coverage. 537 passed, 67 deselected (integration lane), 18 warnings (all ResourceWarning: unclosed sqlite3 connection, from test_live_monitor and test_model_architecture) in 290.45 s. Below 80% per module: traffic_source_service 69%, deployment_service 77%. | Pass |  | test-results/coverage_20261019_104655/pytest-cov.log; evidence: product code = 940e082
2026-10-19 13:00 | ENV-01.9 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Official UNSW_NB15_testing-set.csv (175,341 rows) in research/dataset/raw/ for model B (SYS-01). | Not executed: the file is not on this PC (checked 10:45 and 13:00). An alternative for the model B comparison is to be decided at Checkpoint 1. | Not executed |  | test-results/env_20261019/dataset_counts.json; evidence: product code = 940e082
2026-10-19 13:00 | ENV-01.10 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Second PC for the two-PC pilot confirmed, or reported unavailable to the Test Lead (ENV-01 card). | PC B is not available on 2026-10-19. Reported in this log and in the Test Status Report (DOC-05). Plan section 8 contingency applies: SYS-03 hardware steps Not executed; the automated two-node integration tests (INT-01) cover isolation. | Pass |  | Lead Architect's answer, 2026-10-19 13:00; evidence: product code = 940e082
2026-10-19 13:00 | ENV-02.1 | ENV-02 | Afel Anthonielle V. Quirao | dafe5e5 | GitHub Actions CI is green on the build commit (lint, type check, unit tests, browser polling tests) (ENV-02 card). | CI workflow (windows-latest) failed on cb3bcdb (run 38886300881, 2026-10-16) and on 940e082 (runs 38870178965 on 2026-10-16 and 38017196080 on 2026-10-10). In both 2026-10-16 runs: Lint success, Type check success, Unit tests failure ('Process completed with exit code 1'), Browser polling tests skipped. All six runs listed for main (back to 4c9666c, 2026-10-05) concluded failure. | Fail | DEF-01 | GitHub REST API (unauthenticated) actions/runs and jobs for main; job logs need sign-in (HTTP 403); evidence: product code = 940e082
2026-10-19 13:03 | ENV-02.2 | ENV-02 | Afel Anthonielle V. Quirao | dafe5e5 | Local Supabase stack (supabase start) runs for INT-01 (ENV-02 card). | At 10:53 the Docker engine was not running (npx supabase status: exit 1, 'failed to inspect container health'). After Docker Desktop started: npx supabase start exit 0 (13:02:37), npx supabase status exit 0; db, auth, rest, storage, realtime, kong, studio, pg_meta, inbucket and analytics up. But supabase start listed the Edge Runtime under 'Stopped services' although supabase/config.toml enables it: its container had exited (255) 11 days earlier and was not restarted. The stack was therefore not complete. (This row was first logged as Pass at 13:03; corrected at 13:31 after INT-01.1 showed the cause.) | Fail | DEF-02 | test-results/env_20261019/supabase-status.log; test-results/env_20261019/supabase-start.log; test-results/env_20261019/edge-runtime-restart.log; evidence: product code = 940e082
2026-10-19 13:04 | ENV-01.1 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Windows 11 test PC as in plan 5.1 (PC A: Intel Core i5-13420H, 16 GB RAM, Intel Wi-Fi 6 AX203). | Microsoft Windows 11 Home Single Language, version 26H2, OS build 26300.9711; host SANMIGUEL; Intel Core i5-13420H; 15.7 GB usable RAM; Intel Wi-Fi 6 AX203 (Up). The legacy registry field ProductName still reads 'Windows 10 Home Single Language'; the OS caption reads Windows 11. | Pass |  | test-results/env_20261019/environment.txt; evidence: product code = 940e082
2026-10-19 13:04 | ENV-01.2 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | venv runs Python 3.14.6 with the library versions in requirements-model.lock (plan 5.1). | venv\Scripts\python.exe = Python 3.14.6. numpy 2.5.1, scipy 1.18.0, pandas 3.0.3, scikit-learn 1.9.0, joblib 1.5.3, threadpoolctl 3.6.0 installed, each equal to requirements-model.lock. | Pass |  | test-results/env_20261019/environment.txt; test-results/env_20261019/pip-freeze.txt; evidence: product code = 940e082
2026-10-19 13:04 | ENV-01.5 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Npcap installed (plan 5.1). | Npcap 1.88 installed; npcap service Running (start type System); C:\Windows\System32\Npcap present. | Pass |  | test-results/env_20261019/environment.txt; evidence: product code = 940e082
2026-10-19 13:04 | ENV-01.6 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | Administrator rights available for live capture (plan 5.1). | The Windows account is a member of BUILTIN\Administrators. The terminal used for the automated runs is not elevated (Medium integrity), so it runs with RUN_WINDOWS_CAPTURE_TESTS unset; live capture needs scripts\START_APP.cmd started with 'Run as administrator'. | Pass |  | test-results/env_20261019/environment.txt; evidence: product code = 940e082
2026-10-19 13:26 | TC-13 | UNT-01 | Cel Hendrix N. San Miguel | dafe5e5 | All tests pass; 0 lint and type errors (pytest -q; ruff check .; npm run typecheck; node --test tests/monitor_poll.test.cjs). | pytest -q: 537 passed, 67 deselected (integration lane) in 130.13 s. ruff: All checks passed. pyright: 0 errors, 0 warnings, 0 informations. node --test monitor_poll: 11 pass, 0 fail. No flaky failures, so no re-run was needed. Run with RUN_WINDOWS_CAPTURE_TESTS=0 (terminal not elevated). The runner's 'uncommitted changes' flag refers only to the untracked docs/testing/ and test-results/ records. | Pass |  | test-results/suites_20261019_132412/summary.md and pytest-offline.log, ruff-lint.log, pyright-typecheck.log, node-monitor-poll.log; evidence: product code = 940e082
2026-10-19 13:27 | INT-01.1 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | Integration lane (pytest -m integration) passes against the local Supabase stack (INT-01 card). | 5 failed, 60 passed, 2 skipped, 537 deselected in 54.27 s. All 5 failures are Edge Function calls answered HTTP 503 'name resolution failed' (test_enrollment_administration x4, test_local_supabase_stack::test_edge_function_smoke), because the local Edge Runtime container was not running (DEF-02). Test-environment fault; no product code involved. | Fail | DEF-02 | test-results/suites_20261019_132412/pytest-integration.log; evidence: product code = 940e082
2026-10-19 13:28 | SEC-01.1 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | pip-audit finds no known vulnerability in requirements.txt, or each finding is fixed or justified (SEC-01 card). | python -m pip_audit -r requirements.txt: 'No known vulnerabilities found'. | Pass |  | test-results/suites_20261019_132412/pip-audit.log; evidence: product code = 940e082
2026-10-19 13:29 | ENV-02.2 | ENV-02 | Afel Anthonielle V. Quirao | dafe5e5 | Local Supabase stack (supabase start) runs for INT-01 (ENV-02 card). | Re-check after docker start supabase_edge_runtime_AlgoGuard (13:29:25): container Up; serving account_admin and smoke_test on 127.0.0.1:54321/functions/v1. All configured services running. | Pass | DEF-02 | test-results/env_20261019/edge-runtime-restart.log; evidence: product code = 940e082
2026-10-19 13:30 | INT-01.1 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | Integration lane (pytest -m integration) passes against the local Supabase stack (INT-01 card). | Re-run after the Edge Runtime restart: 65 passed, 2 skipped, 537 deselected in 43.70 s; exit 0. The 2 skips are the Npcap capture tests (INT-01.2). | Pass | DEF-02 | test-results/integration_20261019_132933/pytest-integration.log; evidence: product code = 940e082
2026-10-19 13:30 | INT-01.2 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | Npcap capture integration tests (test_cloud_app_stack live capture, test_maintenance_capture) pass with RUN_WINDOWS_CAPTURE_TESTS=1. | Not executed: both skipped ('Set RUN_WINDOWS_CAPTURE_TESTS=1 on Windows with Npcap.') because the automated runs use a terminal that is not elevated. Can be run from an elevated Command Prompt. | Not executed |  | test-results/integration_20261019_132933/pytest-integration.log; evidence: product code = 940e082
2026-10-19 13:50 | ENV-02.1 | ENV-02 | Afel Anthonielle V. Quirao | dafe5e5 | GitHub Actions CI is green on the build commit (lint, type check, unit tests, browser polling tests) (ENV-02 card). | Re-check with the job logs (gh signed in). Both runs (cb3bcdb 38886300881, 940e082 38870178965): setup-python 'python-version: 3.14' installed CPython 3.14.8; Lint 'All checks passed!'; Type check '0 errors, 26 warnings' (all 26 reportMissingModuleSource for maintainer-only packages); Unit tests '5 failed, 476 passed, 21 skipped, 34 deselected, 40 errors'. 44 of the 45 failures/errors are model_runtime.ModelDeliveryError ('Install the locked Python model runtime' x43, 'Retrain this artifact with the locked model runtime' x1): verify_runtime() requires exactly Python 3.14.6 (DEF-01). The 45th is test_cloud_outbox.py::test_cap_reserves_before_enqueue_and_retry_does_not_consume_slot, 'assert spool.drain()' False at line 55 in both runs (DEF-03). | Fail | DEF-01, DEF-03 | test-results/env_20261019/ci_run_38886300881_cb3bcdb_failed.log; test-results/env_20261019/ci_run_38870178965_940e082_failed.log (gh run view --log-failed)
2026-10-19 15:05 | ENV-01.11 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | App starts on 127.0.0.1:5000 in cloud mode (ENV-01 card; local mode is checked separately in SEC-01 / TC-10). | scripts\START_APP.cmd started python app.py at 15:02:30 (2 processes: venv launcher + interpreter). GET http://127.0.0.1:5000/login -> HTTP 200 'Login ¦ AlgoGuard', heading 'Cloud Pilot Access', e-mail + password form (cloud sign-in). Model cache C:\AlgoGuardPilot\state-PC-A\models holds only 1-9c9f0fb1...joblib (SHA-256 9c9f0fb18524eeda...). | Pass |  | Session check of the /login page and the model cache folder (no credentials read); evidence: product code = 940e082
2026-10-19 15:23 | TC-01 | SMK-01 | John Brian A. Tiopes | dafe5e5 | Known Normal row from algoguard_big.csv on Manual Prediction: verdict Normal; event saved. | Input: first Normal row of datasets/algoguard_big.csv (CSV line 2). Signed in as the PC A analyst, cloud mode. Result: NORMAL, model confidence 84.11%; Model Stacking Ensemble; Deployment #1; latency 147.987 ms; event b0087c8e-f95c-4ce9-aa80-bfa0422f8f73; page: 'Saved on this computer - pending upload', Prediction 'Assigned after upload', Alert 'Not created'. Outbox (read-only, 15:23): event created 15:22:59, status synced, receipt prediction_id 2913, alert_id null, node d535e2fd (PC A), deployment 1. | Pass |  | test-results/smoke_20261019/TC-01_manual_normal.png; local outbox C:\AlgoGuardPilot\state-PC-A\outbox\outbox.sqlite3 (read-only query); evidence: product code = 940e082
2026-10-19 15:29 | TC-02 | SMK-01 | John Brian A. Tiopes | dafe5e5 | Known Attack row from algoguard_big.csv on Manual Prediction: verdict Attack; alert created with confidence. | Input: first Attack row of datasets/algoguard_big.csv (CSV line 3). Result: ATTACK, model confidence 92.95%; Model Stacking Ensemble; Deployment #1; latency 44.745 ms; event 5a86608a-76da-41c6-ba68-4c63e7eccbcb; page: 'Saved on this computer - pending upload', Alert 'Created when the record uploads'. Outbox (read-only, 15:29): event created 15:29:25, status synced, receipt prediction_id 2914, alert_id 2319, node d535e2fd (PC A), deployment 1. | Pass |  | test-results/smoke_20261019/TC-02_manual_attack.png; local outbox (read-only query); evidence: product code = 940e082
2026-10-19 15:35 | SMK-01.3 | SMK-01 | John Brian A. Tiopes | dafe5e5 | Short CSV replay produces alerts with no errors (SMK-01 card). | Live Monitor, Sample replay algoguard_big.csv (5,000 flows), Fast, Sequential, Save attacks; stopped after 386 of 5,000 flows. Screen: Flows Analyzed 386; Attacks 275 (71.24%); Normal 111; Alerts Queued 275; average latency 130.725 ms; Pinned deployment #1; Label mismatches 15; Queued for upload 275; Synced to cloud 275; Pending upload 0; Not stored 0; Upload status active; no error message. Outbox (read-only, 15:35): session c89500d0 holds 275 events, all synced, all 275 receipts carry an alert_id, 15:31:20-15:34:30, deployment 1, node d535e2fd. Observation for USE-01: the Recent Flows time column shows UTC (07:34:30 for 15:34:30 local) without a label. | Pass |  | test-results/smoke_20261019/SMK-01_csv_replay_counters.png and SMK-01_csv_replay_sidepanel.png; local outbox (read-only query); evidence: product code = 940e082
2026-10-19 15:37 | TC-03 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Whole independent set through the saved pipeline: accuracy, F1, attack recall >= 90%; FPR <= 8%; ROC-AUC >= 0.95 (plan 3.3). | Model A = deployed Stacking Ensemble (saved_models/run_3/stacking.joblib, SHA-256 9c9f0fb1...847c = deployment #1, trained 2026-10-08 on algoguard_big.csv). Independent set: 82,332 loaded, 29,089 removed as seen, 53,243 evaluated (20,674 attack / 32,569 normal). Accuracy 81.47% (not met), F1 79.49% (not met), recall 92.44% (met), FPR 25.49% (not met), ROC-AUC 0.9371 (not met); precision 69.72%, specificity 74.51%. Confusion: TN 24,268, FP 8,301, FN 1,563, TP 19,111. Harness check: the same model and code on algoguard_big.csv (seen data) give accuracy 96.98%, F1 97.77%, FPR 4.07%, ROC-AUC 0.9963, so the drop is a generalisation gap, not a scoring error. | Fail | DEF-04, DEF-05, DEF-06, DEF-07 | test-results/evaluation_20261019_153649/ (summary.md, metrics.json, confusion_matrix.csv, console.log, sanity_seen_rows.log); evidence: product code = 940e082
2026-10-19 15:37 | SYS-01.2 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Stacking compared with each single model on the same rows (F1, ROC-AUC, time per row) (SYS-01 card). | Same 53,243 rows. F1 / ROC-AUC / ms per row: Random Forest 0.7957 / 0.9306 / 0.0096; Stacking 0.7949 / 0.9371 / 0.0836; Gradient Boosting 0.7765 / 0.9292 / 0.0037; KNN 0.7629 / 0.8962 / 0.0086; AdaBoost 0.7444 / 0.8907 / 0.0315; Naive Bayes 0.3130 / 0.6108 / 0.0036. Stacking has the best ROC-AUC and ties Random Forest on accuracy (0.8147); Random Forest is marginally higher on F1 and recall. Comparison recorded. | Pass |  | test-results/evaluation_20261019_153649/model_comparison.csv; evidence: product code = 940e082
2026-10-19 15:37 | SYS-01.3 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Recall per attack category measured; categories below 90% flagged (SYS-01 card). | Recall: Analysis 99.76%, Reconnaissance 99.71%, Exploits 98.00%, Backdoor 97.78%, DoS 96.93%, Worms 95.35% (43 rows), Generic 91.27% (802 rows). FLAGGED below 90%: Fuzzers 76.62% (5,064 rows) and Shellcode 89.97% (359 rows). Normal specificity 74.51% (32,569 rows). | Pass |  | test-results/evaluation_20261019_153649/per_category.csv; evidence: product code = 940e082
2026-10-19 15:39 | SYS-01.4 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Re-run with the same seed gives the same numbers (SYS-01 card). | Model A retrained the same way: python train.py datasets/algoguard_big.csv --models-dir saved_models/cycle1_A2 (local run 4, 16.1 s, no --deploy; Stacking test-split F1 95.07%, as recorded for model A). Artifact 8,558,646 bytes, SHA-256 5fc6ee7c... (differs from A only by its stored run metadata). On the independent set: accuracy 0.8147, F1 0.7949, recall 0.9244, FPR 0.2549, ROC-AUC 0.9371, confusion 24,268 / 8,301 / 1,563 / 19,111 - identical to A. Row by row on 53,243 rows: 0 verdicts differ; max attack-probability difference 0.0. | Pass |  | test-results/evaluation_20261019_153850/ (summary.md, console.log, train_A2_console.log, A_vs_A2_row_by_row.json); evidence: product code = 940e082
2026-10-19 15:50 | SYS-01.5 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Model B (comparison only) trained from the UNSW-NB15 training file with train.py, no --deploy, training time recorded; usable for an A-vs-B comparison on unseen data (Master Prompt Phase 4). | Official testing set unavailable, so B was trained on the training file minus a seeded 30% key-group hold-out (66,393 rows; hold-out 15,939 rows, 0 overlap). python train.py research/dataset/processed/sys01_holdout/model_b_train.csv --models-dir saved_models/cycle1_B: local run 5, 152 s, exit 0. train.py used all 44 non-target columns as features, including attack_cat (encodes the label) and id; Random Forest, AdaBoost, Gradient Boosting, Naive Bayes and Stacking all reported 100.00% accuracy / F1 / ROC-AUC (Naive Bayes scored 48.72% on model A's data). evaluate_model.py refused the artifact ('expects different features'). Not usable; a 15-feature model B was trained instead (SYS-01.6). | Fail | DEF-08 | test-results/sys01_holdout/train_B_console.log, eval_B_raw_console.log, holdout_manifest.json; saved_models/cycle1_B/run_5 (git-ignored); evidence: product code = 940e082
2026-10-19 15:59 | SYS-01.6 | SYS-01 | Victor Alexander A. Ong | dafe5e5 | Comparison only (not the official result): model A and model B evaluated on the same unseen rows (Master Prompt Phase 4, adapted: hold-out instead of the official testing set). | Model B = 15-feature retrain on the same 66,393 rows (local run 6, 809.9 s; test-split Stacking F1 95.42%). Hold-out 15,939 rows (6,174 attack / 9,765 normal), 0 removed as seen by either model. A: accuracy 81.69%, F1 79.56%, recall 92.03%, FPR 24.85%, ROC-AUC 0.9375, 0.144 ms/row. B: accuracy 90.79%, F1 87.36%, recall 82.18%, FPR 3.77%, ROC-AUC 0.9713, 0.236 ms/row. B cuts false positives (2,427 -> 368) but misses more attacks (492 -> 1,100 FN); B recall Fuzzers 49.47%, Shellcode 59.29%. A on the hold-out matches its official 53,243-row result within 0.6 points. | Pass |  | test-results/sys01_holdout/ (eval_A_on_holdout/, eval_B_on_holdout/, *_console.log, holdout_manifest.json, model_b_train_15_manifest.json, train_B15_console.log, make_holdout.py, make_b15.py); evidence: product code = 940e082
2026-10-19 16:16 | INT-01.3 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | Preprocessing to Stacking to alert path verified; Stacking uses all five base models and the Logistic Regression final estimator; model delivery, publication and outbox unit tests pass (INT-01 card). | pytest -q tests/test_model_delivery.py tests/test_model_publication.py tests/test_cloud_outbox.py tests/test_model_architecture.py: 42 passed in 39.49 s (includes test_stacking_uses_five_models_and_logistic_regression). Deployed artifact (run_3/stacking.joblib, SHA-256 9c9f0fb1...): pipeline preprocessor -> StackingClassifier with fitted RandomForestClassifier, GradientBoostingClassifier, AdaBoostClassifier, KNeighborsClassifier, GaussianNB; final estimator LogisticRegression; cv 5, predict_proba stacking. End-to-end path to alert shown by TC-02 (alert #2319). | Pass |  | test-results/int01_20261019_161543/pytest-int01-units.log, inspect_stacking_modelA.log, inspect_stacking.py; evidence: product code = 940e082
2026-10-19 17:03 | TC-08 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | One byte changed in the cached artifact (local copy, backed up); app restarted: SHA-256 mismatch reported; model not loaded. | App stopped 16:58 (outbox 919 synced, 0 pending). Cache backed up to C:\AlgoGuardPilot\TC08-backup-models-20261019 (SHA-256 verified equal). Byte at offset 4,279,323 of 1-9c9f0fb1...joblib changed 0x00 -> 0x01 (SHA-256 now c8f1c7fe..., size unchanged). App restarted 17:00:30, PC A analyst signed in. Predict page: 'No active deployment - The cached model is corrupt. Remove it and retry.'; no form, no prediction possible. Live Monitor: the same message, no capture controls. The app neither deleted nor replaced the file. Dashboard still showed the cloud deployment as 'Deployed' with no local warning (DEF-09, Low). | Pass | DEF-09 | test-results/int01_20261019_161543/tc08_corruption.json, TC-08_predict_refused.png, TC-08_live_monitor_refused.png, TC-08_dashboard_while_corrupt.png, tc08_flip_byte.py; evidence: product code = 940e082
2026-10-19 17:12 | TC-08 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | After restoring the backup, the app loads the model again (Master Prompt Phase 5.3). | App stopped; backup copied back at 17:07; cached file SHA-256 9c9f0fb1...847c again (8,558,646 bytes, only file in the cache). App restarted as administrator, PC A analyst signed in. Predict form shown again; Run Prediction: green verdict at 50.46% confidence, Stacking Ensemble, Deployment #1, latency 2,021.727 ms (first prediction after start), event 3f69afc9..., synced as prediction #3190, no alert. The confidence differs from TC-01 (84.11%): the screenshot shows sinpkt typed as 133.42319, but offline re-scoring of the exact row and of that variant both give Normal 84.11%, so another typed value (not visible, and cleared from the outbox after sync) probably differed. Not counted as a defect; the model loaded and classified. | Pass |  | test-results/int01_20261019_161543/TC-08_after_restore_prediction.png, tc08_recheck_row.py, tc08_recheck_row.log; evidence: product code = 940e082
2026-10-19 17:21 | TC-09 | INT-01 | Afel Anthonielle V. Quirao | dafe5e5 | CSV replay running in cloud mode; disconnect, restart, reconnect, sign in: pending events kept and synced once; no duplicates. | Baseline 17:15: outbox 920 synced, 0 pending. Live Monitor replay (algoguard_big, Fast, Sequential, Save every flow) started; Wi-Fi switched off (not Airplane mode). Offline: new flows marked Pending; side panel Queued 142, Synced 39, Pending 103, Not stored 0, Upload status 'retrying (transient)'. Capture stopped and app closed offline; app restarted offline: sign-in refused with 'The cloud is unreachable. Online sign-in is required; a cached model does not permit offline access.' (by design); a page showed 'The cloud is unavailable. Pending records stay on this computer.' Wi-Fi on, signed in: Dashboard 17:21 showed Pending 63 durable, Synced 417, Rejected 0, Not stored 0. Outbox 17:21:28: capture session 4ea6f1f9 holds 202 events (17:17:43-17:19:28), all synced, 0 pending; outbox total 1,122 = 920 + 202. 202 distinct event UUIDs and 202 distinct cloud prediction ids, contiguous #3191-#3392; 145 distinct alert ids. No duplicates, none lost. | Pass |  | test-results/int01_20261019_161543/TC-09_*.png (sign-in screenshot e-mail redacted), tc09_outbox_check.json, tc09_outbox_sessions.txt; evidence: product code = 940e082
2026-10-19 17:24 | SEC-01.2 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | CSRF: missing or forged tokens refused; sign-in throttle logic (SEC-01 card; Master Prompt: pytest tests/test_api_validation.py tests/test_login_throttle.py). | 25 passed in 31.52 s: invalid JSON bodies rejected before any action (16 cases), JSON actions require a JSON content type (2), invalid or forged login tokens return a client error (3); throttle: repeated failures pause the account then release it, success clears the counter, one address cannot spray many usernames, old failures are forgotten. Cookie writes without a CSRF token are also covered by tests/test_cloud_app.py::test_cookie_writes_require_csrf_but_bearer_api_calls_do_not, which passed in TC-13. | Pass |  | test-results/sec01_20261019_172340/pytest-csrf-throttle.log; evidence: product code = 940e082
2026-10-19 17:31 | SEC-01.3 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | Bandit run; every Medium/High finding fixed or justified, or a defect raised (SEC-01 card; Master Prompt Phase 6). | Bandit (13:28 scan) by severity: High 0, Medium 14, Low 18. All 14 Medium findings read in the source and justified as false positives: 3 x B104 are an outgoing socket bound to an ephemeral port before connect (cloud_connections.py:177, maintenance_connections.py:141) and a host-name list (maintainer_env.py:44) - nothing listens; 11 x B608 build SQL only from fixed table/column lists or '?' placeholders, with every value passed as a parameter (cloud_outbox.py, legacy_backup.py, legacy_import.py, database_service.py). Hardening suggestion (not a defect): call icacls by full path in cloud_outbox.py:55. No defect raised. | Pass |  | test-results/sec01_20261019_172340/bandit_review.md; test-results/suites_20261019_132412/bandit.log; evidence: product code = 940e082
2026-10-19 17:33 | SEC-01.4 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | Secrets: git ls-files lists only the .env .example files; git grep for sb_secret_ / service_role / JWT-like strings finds nothing outside tests/fixtures (Master Prompt Phase 6). | Tracked .env files: .env.example and .env.maintainer.example only. git grep (HEAD): 21 hits, 0 JWT-like strings. Outside tests: service_role is the Postgres role name in 14 migration lines, supabase/config.toml:24 (comment) and docs/migration/05b-access.md:606 (prose); scripts/run_test_suites.py:37 is the redaction regex. Tests: test_cloud_schema.py, test_cloud_app.py, test_cloud_repository.py (fixtures). No secret values found; values were not printed. | Pass |  | Session check with values masked (git ls-files, git grep); evidence: product code = 940e082
2026-10-19 17:41 | TC-06 | SYS-03 | Cel Hendrix N. San Miguel | dafe5e5 | Live re-run: analyst A requests node B's alerts in the UI and Data API: no rows returned; no private data in errors. | Not executed: second PC not available (ENV-01.10). Covered by the pilot (SYS-03.P1, SYS-03.P2) and by the automated two-node lane, which passed at 13:30: tests/integration/test_two_node_acceptance.py::test_two_independent_nodes_download_and_write_concurrently and tests/integration/test_relational_access.py (4 tests) against the local Supabase stack. | Not executed |  | test-results/integration_20261019_132933/pytest-integration.log; evidence: product code = 940e082
2026-10-19 17:41 | TC-07 | SYS-03 | Cel Hendrix N. San Miguel | dafe5e5 | Live re-run: administrator revokes B; B tries prediction and capture: both refused; Restore re-enables. | Not executed: second PC not available (ENV-01.10). Covered by the pilot (SYS-03.P3) and by tests/integration/test_relational_access.py::test_protected_tables_views_and_revocation, which passed at 13:30. | Not executed |  | test-results/integration_20261019_132933/pytest-integration.log; evidence: product code = 940e082
2026-10-19 17:42 | TC-15 | UAT-01 | Pauleen Joy O. Gomez | dafe5e5 | Product Owner, signed in as an analyst, replays algoguard_big.csv, opens an alert, acknowledges and resolves it: alerts raised for attacks; review actions logged; Product Owner accepts. | Not executed: awaiting Product Owner. Four scenarios written for her (replay detection, alert review, report from alerts, administrator approves a node member) with Pass/Fail lines and the accept/reject signature. On 2026-10-20 the Lead Architect relayed that she gave permission to accept the build; no executed scenarios or signed decision were received. | Not executed |  | docs/testing/cycle-1/UAT scenarios.md; evidence: product code = 940e082
2026-10-20 04:51 | ENV-01.11 | ENV-01 | Arella Biacea B. Mirasol | dafe5e5 | App starts in local (SQLite) mode (ENV-01 card). | ALGOGUARD_DB_MODE=sqlite and ALGOGUARD_PORT=5001 set for that process only (.env untouched); python app.py served http://127.0.0.1:5001; /login -> HTTP 200 'Login ¦ AlgoGuard', heading 'Local Console Access' with a username field. Port 5001 was used so the cloud-mode app on 5000 kept running. | Pass |  | Session check of the local /login page; evidence: product code = 940e082
2026-10-20 04:51 | TC-10 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | Local mode, account exists: five wrong passwords for one account -> further attempts paused. | Against the local-mode app on port 5001, account 'admin' (the only local account), six sign-ins with made-up wrong passwords sent by script: attempts 1-5 HTTP 200 'Invalid username or password.'; attempt 6 HTTP 429 'Too many failed sign-in attempts. Try again in 15 minutes.' Local system_log: five login_failed (log 115-119) and login_throttled 'Sign-in for admin blocked for 15 minutes after repeated failures.' (log 120), 20:51:21-20:51:23 UTC. The app does not check the password while locked (app.py:398-406), so a correct password would get the same reply; that was not demonstrated because no real password was used. The local app was stopped afterwards, which clears the in-memory lockout. Deviation: the existing admin account was used instead of a throwaway account created on the Admins page. | Pass |  | test-results/sec01_20261019_172340/tc10_lockout.py, tc10_lockout_result.log, tc10_local_db_events.txt; evidence: product code = 940e082
2026-10-20 04:52 | SEC-01.5 | SEC-01 | Arella Biacea B. Mirasol | dafe5e5 | Analyst role cannot reach administrator pages: signed in as an analyst, /admins and /nodes refused (SEC-01 card; Master Prompt Phase 6). | Local mode (port 5001): throwaway Analyst 'cycle1_roles_test' created in the local SQLite database with a random password held only in memory; signed in -> Dashboard. GET /admins -> HTTP 302 to / with 'Only Administrator accounts can manage admin users.'; GET /nodes -> 404 (Nodes exists only in cloud mode). (/dashboard -> 404 is a wrong path in the check script; the Dashboard is /.) Cloud mode with a real analyst was not checked by hand; it is covered by tests/test_cloud_app.py::test_administrator_account_management_uses_the_checked_function (a demoted administrator gets 302 from /admins and loses the Accounts link) and the integration tests test_a_token_claiming_administrator_is_not_an_administrator and test_a_profile_cannot_grant_itself_a_role, which passed on 2026-10-19. The local account cycle1_roles_test remains (the app has no delete function). | Pass |  | test-results/sec01_20261019_172340/roles_check.py, roles_check_result.json; evidence: product code = 940e082
2026-10-20 04:54 | TC-05 | SYS-02 | John Brian A. Tiopes | dafe5e5 | POST /predict (and Manual Prediction) with a missing field, text in a numeric field, an out-of-range number: rejected with a plain message; nothing stored. | Server side, through services.simulation_service.predict_with_artifact (used by app.py /simulation and /predict and cloud_app.py:416) with model A, starting from the TC-01 row (control: Normal 84.11%): missing dur -> ACCEPTED, filled with the training default, Normal 56.67%; empty dur -> ACCEPTED, 56.67%; spkts 'abc' -> REJECTED 'spkts must contain a finite numerical value.'; sbytes '1e308' -> REJECTED but with 'Prediction failed: Input X contains infinity or a value too large for dtype('float32').'; sbytes '-5' -> ACCEPTED, Normal 86.65%. Accepted input is classified and queued for upload (cloud_app.py:415-418); the cloud form also fills absent fields with defaults (cloud_app.py:608-611). In the browser, the form's required and number-type boxes block a missing value and 'abc', but there are no min/max limits, so '1e308' and '-5' reach the server. The browser part was not run by hand. | Fail | DEF-12, DEF-13 | test-results/sys02_files/tc05_server_validation.py, tc05_server_validation_result.json; templates/simulation.html; evidence: product code = 940e082
2026-10-20 04:55 | TC-04 | SYS-02 | John Brian A. Tiopes | dafe5e5 | Synthetic PCAP, persistence All: all flows classified and saved. | Service level, this cycle: captures/cycle1-tc04-sample.pcap (write_sample_pcap, 10 sessions) through PcapReplaySource and predict_with_artifact with model A: 82 packets -> 11 flows, all classified (10 Attack, 1 Normal; end reasons fin, flush) - the same 11 flows the pilot recorded. Saving was not exercised here. Pilot Test B (2026-10-08, 4c9666c) replayed the same PCAP through the Live Monitor on both PCs: '11 ¦ 11 ¦ 11 -> 0 ¦ 0 of 82 packets' stored -> synced. | Pass |  | test-results/sys02_files/sys02_pcap_service_check.py, sys02_pcap_service_check_result.json, sys02_files_manifest.json; docs/migration/05f-pilot.md §3 Test B; evidence: product code = 940e082
2026-10-20 04:55 | SYS-02.1 | SYS-02 | John Brian A. Tiopes | dafe5e5 | Bad files (empty, text, truncated PCAP) rejected without a crash (SYS-02 card). | Service level (PcapReplaySource): cycle1-bad-empty.pcap refused 'Unable to read the packet capture: No data could be read!'; cycle1-bad-text.pcap refused 'Unable to read the packet capture: Not a supported capture file'; cycle1-bad-truncated.pcap NOT refused - 49 packets read, 7 flows classified, only a console warning 'Pcap: packet has been truncated'. No crash in any case. The Live Monitor messages for these files were not observed by hand. | Fail | DEF-14 | test-results/sys02_files/sys02_pcap_service_check_result.json; evidence: product code = 940e082
2026-10-20 04:56 | SYS-02.2 | SYS-02 | John Brian A. Tiopes | dafe5e5 | Live Npcap capture classifies flows and saves results; AlgoGuard's own cloud traffic is excluded (SYS-02 card). | Not executed this cycle on PC A: live capture needs the app run as administrator and a person at the Live Monitor, and no results were received by close. Pilot evidence: PC A capture 10 (2026-10-15, Administrator) 27 flows, 18 stored, '0 of 848 packets' dropped, '329 own cloud packets excluded'; check_capture_exclusion.py on 2026-10-16 'passed: true' on both PCs ('owned flows classified 0; unrelated flows classified 10'). | Not executed |  | docs/migration/05f-pilot.md §3 Test D; evidence: product code = 940e082
2026-10-20 04:56 | SYS-02.3 | SYS-02 | John Brian A. Tiopes | dafe5e5 | 300-event persistence cap shown in the UI (SYS-02 card). | Not executed this cycle: no replay this cycle reached 300 stored events (SMK-01 stored 275, TC-09 202) and no capped replay was run by close. Automated: tests/test_live_monitor.py asserts persisted <= MAX_PERSISTED_PER_SESSION (passed in TC-13). Pilot: captures 4 and 5 stored '300 (cap)' of 5,000 flows each, and an unplanned replay 'classified 571 flows and stored exactly 300'. | Not executed |  | docs/migration/05f-pilot.md §3 (Test C, incidental cap evidence); evidence: product code = 940e082
2026-10-20 04:56 | PRF-01.1 | PRF-01 | Afel Anthonielle V. Quirao | dafe5e5 | Sustained events per second, per client >= 20 (plan 3.4). | Measured from this cycle's Fast CSV replays on PC A: TC-09 (Save every flow) 202 events queued 17:17:43-17:19:28 = 105 s -> 1.92 events/s; SMK-01 386 flows analysed in about 190 s (stored events 15:31:20-15:34:30) -> about 2.0 flows/s. The CSV source is paced at one flow per 0.35 s (<= 2.86/s), so 20/s cannot be reached with the shipped sources - same cause as pilot limit L1. | Fail | DEF-11 | test-results/int01_20261019_161543/tc09_outbox_sessions.txt; Test Log SMK-01.3; services/live_monitor_service.py SPEED_CHOICES; evidence: product code = 940e082
2026-10-20 04:56 | TC-11 | PRF-01 | Afel Anthonielle V. Quirao | dafe5e5 | Live capture of ordinary browsing: event-to-verdict lag p95 <= 500 ms (excluding flow timeouts). | Not executed: needs a live capture from an elevated app with someone browsing, and no results were received by close. Measurement note: the app stores no flow end time or per-flow lag (local SQLite stamps flows at classification; the outbox clears payloads after upload), so the lag can only be collected from the live /monitor/status feed (detection_lag_ms, end_reason); test-results/prf01/tc11_collect_lag.js was prepared for that. Pilot reference (different budget): average live lag 13.1 s on PC B including the 15 s idle timeout. | Not executed |  | test-results/prf01/tc11_collect_lag.js; evidence: product code = 940e082
2026-10-20 04:56 | PRF-01.2 | PRF-01 | Afel Anthonielle V. Quirao | dafe5e5 | Packet drop during live capture <= 1%; 30-minute soak: CPU <= 80%, RAM <= 1 GiB, no steady growth (plan 3.4). | Not executed this cycle: both need a live capture / 30-minute replay started from the browser, and no results were received by close (test-results/prf01/soak_sampler.py was prepared and trial-run: idle app 0.7-1.1% CPU, ~259 MB). Pilot reference (different budgets): packet drop 0% on both PCs; CPU peak 24.5% / 6.3%; RAM peak 294 / 108 MB. | Not executed |  | test-results/prf01/soak_sampler.py; docs/migration/05f-pilot.md §4; evidence: product code = 940e082
2026-10-20 04:56 | TC-12 | USE-01 | Brynt M. Timtiman | dafe5e5 | Every page at 390 px (and 1366 px): no page-level horizontal scroll; accessibility scan on Login, Live Monitor and Manual Prediction. | Not executed in this log: no results (screenshots, widths, Lighthouse scores) were received by the log keeper. The Testing Kanban shows USE-01 moved to Done with all four boxes ticked by the card's side on 2026-10-19/20; the log and the board disagree until those results are added. Observation from other cases: alert, log and feed times are shown in UTC without saying so, while 'Deployed at' says UTC. | Not executed |  | Testing Kanban USE-01 card (no attached results); evidence: product code = 940e082
2026-10-20 05:01 | REG-01.1 | REG-01 | Cel Hendrix N. San Miguel | 503cb9b | Full automated suite re-run on the release-candidate commit; no new failures (REG-01 card; TC-14 second half). | Release candidate 503cb9b = product code 940e082 + the accessibility fix for DEF-15 (templates/monitor.html, static/css/style.css), committed 2026-10-19 19:48 from the USE-01 owner's account and pulled to PC A. run_test_suites.py --all: pytest 537 passed / 67 deselected; ruff all checks passed; pyright 0 errors; node 11 pass; integration 65 passed, 2 skipped (Npcap capture tests, terminal not elevated); pip-audit no known vulnerabilities; Bandit High 0 / Medium 14 / Low 18 - the same findings reviewed in SEC-01.3. No new failures. | Pass | DEF-15 | test-results/suites_20261020_045724/summary.md and step logs; evidence: product code = 940e082
2026-10-20 05:03 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 503cb9b | DEF card marked fixed with its commit: failing case re-run on the fix commit, then the full automated suite: case passes; no new failures. | Only DEF-15 was fixed during the cycle (503cb9b). The fix is present on the release candidate (the Live Monitor feed container now has tabindex="0", role="region", aria-label="Live monitor feed" and a :focus-visible outline) and the full suite passed on it (REG-01.1). The failing case itself - the Lighthouse accessibility audit of the signed-in Live Monitor page - was not re-run: it needs a signed-in browser and no Lighthouse report was received. DEF-15 stays 'Fixed, re-test pending'. No other defect was fixed in cycle 1. | Not executed | DEF-15 | git show 503cb9b; test-results/suites_20261020_045724/; evidence: product code = 940e082
2026-10-20 05:03 | REG-01.2 | REG-01 | Cel Hendrix N. San Miguel | 503cb9b | SMK-01 re-run on the final build (REG-01 card). | Not executed: needs a person at the app (sign-in, Manual Prediction, CSV replay) and was not done by close. The change since SMK-01 touches only the Live Monitor feed's markup and CSS; prediction and storage code are unchanged and the full suite passed on 503cb9b. | Not executed |  | git diff 940e082 503cb9b
2026-10-20 06:06 | REG-01.2 | REG-01 | Cel Hendrix N. San Miguel | 503cb9b | SMK-01 re-run on the final build (REG-01 card). | App restarted as administrator on 503cb9b; PC A analyst signed in once in a test Chrome window driven by script (Playwright over CDP). TC-01 Normal row -> NORMAL 84.11%, deployment #1, synced as prediction #4160, no alert. TC-02 Attack row -> ATTACK 92.95%, synced as prediction #4161 with alert #3369. Short replay (algoguard_big, Fast, Save attacks, 120 s): 172 flows, 126 Attack / 46 Normal, 126 alerts, 126 queued, 126 synced, 0 pending, 0 not stored, no error. Two earlier attempts at 05:53-05:54 failed on a screenshot step after submitting; their 3 manual predictions were synced and are extra records, not results. | Pass |  | test-results/ui_20261020/smk_rerun.json, smk_*.png, outbox_sessions_0600.txt; evidence: product code = 940e082
2026-10-20 06:08 | TC-05 | SYS-02 | John Brian A. Tiopes | 503cb9b | Malformed input on Manual Prediction: missing field, text in a numeric field, an out-of-range number, a negative byte count - rejected with a plain message; nothing stored. | Real form, starting from the TC-01 row: (a) dur emptied -> browser blocks the submit, 'Please fill out this field.'; (b) typing 'abc' into spkts leaves it empty -> 'Please fill out this field.'; (c) sbytes 1e308 -> 'Prediction failed: Input X contains infinity or a value too large for dtype('float32').' (DEF-13); (d) sbytes -5 -> ACCEPTED, NORMAL 86.65%, event cb1438e0, stored and synced as prediction #4288 (DEF-12). (a) and (b) are stopped only by the browser; the server accepts them (TC-05 at 04:54). | Fail | DEF-12, DEF-13 | test-results/ui_20261020/sys02_ui.json, tc05_*.png; evidence: product code = 940e082
2026-10-20 06:08 | TC-04 | SYS-02 | John Brian A. Tiopes | 503cb9b | Synthetic PCAP, persistence All: all flows classified and saved. | Live Monitor, Recorded packets (PCAP), cycle1-tc04-sample.pcap, Fast, Save every flow: 11 of 11 flows, 10 Attack / 1 Normal, 10 alerts, 11 queued, 11 synced, 0 pending, 0 not stored; 'The traffic source finished streaming.' | Pass |  | test-results/ui_20261020/sys02_ui.json, pcap_cycle1-tc04-sample.png; evidence: product code = 940e082
2026-10-20 06:08 | SYS-02.1 | SYS-02 | John Brian A. Tiopes | 503cb9b | Bad files (empty, text, truncated PCAP) rejected without a crash (SYS-02 card). | Live Monitor: cycle1-bad-empty.pcap -> 'Unable to read the packet capture: No data could be read!'; cycle1-bad-text.pcap -> 'Unable to read the packet capture: Not a supported capture file'; cycle1-bad-truncated.pcap -> 7 of 7 flows streamed and saved, 'The traffic source finished streaming.', no warning (DEF-14). No crash; the page kept working. | Fail | DEF-14 | test-results/ui_20261020/sys02_ui.json, pcap_*.png; evidence: product code = 940e082
2026-10-20 06:15 | SYS-02.3 | SYS-02 | John Brian A. Tiopes | 503cb9b | 300-event persistence cap shown in the UI (SYS-02 card). | Sample replay algoguard_big, Fast, Save every flow: side panel 'Queued for upload 300 (capped)', 'Not stored 312', classification continued to 612 flows (438 Attack); 211 alerts; Synced 300, Pending 0. Outbox: session 749511b1 holds exactly 300 events, all synced, 211 with alerts. The cap is shown in the Queued-for-upload field; no separate message. | Pass |  | test-results/ui_20261020/sys02_ui.json, cap_300.png, outbox_sessions_0600.txt; evidence: product code = 940e082
2026-10-20 06:19 | TC-12 | USE-01 | Brynt M. Timtiman | 503cb9b | Every page at 390 px (and 1366 px): no page-level horizontal scroll. | Dashboard, Live Monitor, Manual Prediction, Alerts, System Logs, Reports, Nodes, Accounts/Admins and Login at 1366x768 and 390x844 (fresh tab, signed-in session): document scrollWidth never above the window width (375-390 of 390; 1351-1366 of 1366), no element outside a scroll container past the right edge; screenshots show stacked layouts with no overlap. Accounts/Admins redirects the analyst to the Dashboard. | Pass |  | test-results/ui_20261020/use01/use01_ui.json and 18 screenshots; evidence: product code = 940e082
2026-10-20 06:19 | USE-01.1 | USE-01 | Brynt M. Timtiman | 503cb9b | Keyboard navigation and form labels checked on Login, Live Monitor and Manual Prediction (USE-01 card). | Tab walk: Login 3 of 3 interactive elements reached, Live Monitor 17 of 17, Manual Prediction 25 of 25 distinct (26 counting a second 'Live Monitor' link); no visible field without a label (label element, aria-label or aria-labelledby). | Pass |  | test-results/ui_20261020/use01/use01_ui.json; evidence: product code = 940e082
2026-10-20 06:23 | USE-01.2 | USE-01 | Brynt M. Timtiman | 503cb9b | Automated accessibility scan run; serious issues logged as DEF cards (USE-01 card). | Lighthouse 12.6.0, desktop, Accessibility only: Login 100 (signed-out Chrome), Live Monitor 100 and Manual Prediction 100 (signed-in session, storage reset disabled); 0 failed audits on each. | Pass |  | test-results/ui_20261020/lighthouse/ (reports and lighthouse_summary.json); evidence: product code = 940e082
2026-10-20 06:24 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 503cb9b | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-15 re-test on 503cb9b: the Live Monitor feed has tabindex=0, role=region, aria-label 'Live monitor feed'; reached with Tab (17th stop); PageDown scrolled it from 0 to 420 px of 2,084 px content; visible focus outline (solid 1.6px). Lighthouse 12.6 has no scrollable-region audit, so the behaviour was tested directly. Full suite passed on 503cb9b (REG-01.1). DEF-15 closed. | Pass | DEF-15 | test-results/ui_20261020/def15_check.json, def15_feed_focused.png; evidence: product code = 940e082
2026-10-20 06:26 | SYS-02.2 | SYS-02 | John Brian A. Tiopes | 503cb9b | Live Npcap capture classifies flows and saves results; AlgoGuard's own cloud traffic is excluded (SYS-02 card). | Live interface capture, default interface, Save attacks, 06:24:38-06:26:08 (90 s) while about 100 public web pages were fetched: 8,721 packets, 0 dropped, 1,025 own cloud packets excluded; 139 flows classified (93 Attack / 46 Normal; ended by FIN 14, RST 18, idle timeout 107); 93 saved, 93 synced, 0 pending. Observation: 67% of ordinary browsing flagged Attack - same pattern as pilot finding 12 and consistent with DEF-06. | Pass |  | test-results/ui_20261020/tc11_live.json, live_capture.png; evidence: product code = 940e082
2026-10-20 06:26 | TC-11 | PRF-01 | Afel Anthonielle V. Quirao | 503cb9b | Live capture of ordinary browsing: event-to-verdict lag p95 <= 500 ms (excluding flow timeouts). | Same 90 s capture. Lag per flow read from the page's /monitor/status feed (detection_lag_ms = verdict time minus the flow's last packet). Flows ended by TCP FIN/RST (no timeout wait), n=32: p50 388.9 ms, p95 895.6 ms - budget missed. All 139 flows: p50 15,765 ms, p95 16,311 ms (includes the 15 s idle timeout); idle-timeout flows minus 15 s: p50 916.5 ms, p95 1,362.4 ms. Model latency: p50 163.9 ms, p95 377.2 ms. A traffic generator and Chrome were running on PC A. | Fail | DEF-17 | test-results/ui_20261020/tc11_live.json; evidence: product code = 940e082
2026-10-20 06:26 | PRF-01.3 | PRF-01 | Afel Anthonielle V. Quirao | 503cb9b | Packet drop fraction during live capture <= 1% (plan 3.4). | 0 of 8,721 packets dropped (0%) in the 90 s live capture. | Pass |  | test-results/ui_20261020/tc11_live.json (session_capture_counters); evidence: product code = 940e082
2026-10-20 06:27 | USE-01.3 | USE-01 | Brynt M. Timtiman | 503cb9b | Error messages and status text are plain language (USE-01 card). | Mostly plain (e.g. 'Unable to read the packet capture: Not a supported capture file', 'Please fill out this field.'). Not plain: the 1e308 message 'Input X contains infinity or a value too large for dtype('float32')' (DEF-13); System Logs show the word 'None' as the message of every flow_accepted entry (DEF-18); feed, alert and log times are UTC without a label - the newest log line reads 2026-10-19 22:15:46 for 2026-10-20 06:15:46 local (DEF-16). | Fail | DEF-13, DEF-16, DEF-18 | test-results/ui_20261020/use01/1366_logs.png, use01/390_monitor.png, tc05_c_1e308.png; evidence: product code = 940e082
2026-10-20 06:57 | PRF-01.4 | PRF-01 | Afel Anthonielle V. Quirao | 503cb9b | 30-minute soak: AlgoGuard process CPU <= 80% and RAM <= 1 GiB, no steady growth (plan 3.4; PRF-01 card). | Live Monitor, Sample replay algoguard_biggest.csv, Fast, Sequential, Save attacks, 06:27:23-06:57:25 (1,800 s), started and stopped by script in the signed-in test Chrome. Sampler every 30 s on the app (PID 37452 + its 3.5 MB launcher, found by command line), 60 samples 06:28:02-06:57:33. CPU (share of the whole machine): max 8.03%, mean 7.54%. RAM: max 352.2 MB (first 4 minutes), dropped to 298.6 MB at 06:32, climbed to 327.8 MB by 06:55 (about 1.1 MB/min), flat from 06:52 (+1 MB), 322.0 MB at the end; whole-run trend -0.1 MB/min. Threads 35-37. No error message; 300 stored (cap), 300 synced, 0 pending. Observation: 30 minutes cannot rule out a slow leak after the 06:32-06:52 climb; a longer soak is suggested for cycle 2. Short test runs in other processes ran on PC A during the soak. | Pass |  | test-results/soak_20261020_062732.csv; test-results/ui_20261020/soak_ui.json, soak_sampler_console.log, soak_end.png; evidence: product code = 940e082
2026-10-20 06:57 | PRF-01.5 | PRF-01 | Afel Anthonielle V. Quirao | 503cb9b | Sustained events per second, per client >= 20 (plan 3.4). | Same 30-minute Fast replay: 2,972 flows classified in 1,800 s = 1.65 flows/s (five-minute readings 498, 1,025, 1,548, 2,043, 2,477, 2,972); 300 events stored (the per-session cap), all synced. The sample source is paced at one flow per 0.35 s (<= 2.86/s), so 20/s cannot be reached with it. | Fail | DEF-11 | test-results/ui_20261020/soak_ui.json, soak_end.png; evidence: product code = 940e082
2026-10-20 07:01 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 0480899 | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-09 (fixed in eecaac7 and 0480899) re-tested with the TC-08 procedure on a backed-up cache: cache file 1-9c9f0fb185... (8,558,646 bytes) copied to C:\AlgoGuardPilot\REG01-backup-models-20261020 (SHA-256 checked), one byte changed at offset 4,279,323; app restarted on 0480899 and the PC A analyst signed in. Dashboard: model label 'Unavailable here' and 'Not usable on this computer: The cached model is corrupt. Remove it and retry.'; Manual Prediction: 'No active deployment - The cached model is corrupt. Remove it and retry.' Cache restored from the backup at 07:01:18 (SHA-256 matches again), no restart needed: Dashboard 'Deployed', Manual Prediction form back with 15 fields. DEF-09 closed. | Pass | DEF-09 | test-results/ui_20261020/reg01/def09_check.json, def09_dashboard_corrupt.png, def09_dashboard_restored.png; evidence: product code = 940e082
2026-10-20 07:02 | TC-05 | SYS-02 | John Brian A. Tiopes | 0480899 | Malformed input on Manual Prediction: missing field, text in a numeric field, an out-of-range number, a negative byte count - rejected with a plain message; nothing stored. | Re-run of (c) and (d) on the fix build, signed-in test Chrome, starting from the TC-01 row: (c) sbytes 1e308 -> 'sbytes is too large to classify; enter a smaller value.'; (d) sbytes -5 -> browser: 'Value must be greater than or equal to 0.'; the same form with the browser check off -> 'sbytes cannot be negative.'; /predict with sbytes -5, dur -1 and sbytes 1e308 -> HTTP 400 with the same plain messages. Flows Analyzed 2,277 before and after: nothing stored. (a) and (b) not re-run (browser-blocked at 06:08; unchanged). Still failing: a missing or empty numeric field sent to the server is filled with the training default and stored - unchanged design, asserted by test_missing_numeric_prediction_is_imputed_and_saved_as_null, which passed on this build (REG-01.1). | Fail | DEF-12 | test-results/ui_20261020/reg01/reg01_ui.json (tc05), tc05_*.png; evidence: product code = 940e082
2026-10-20 07:02 | SYS-02.1 | SYS-02 | John Brian A. Tiopes | 0480899 | Bad files (empty, text, truncated PCAP) rejected without a crash (SYS-02 card). | Live Monitor, Recorded packets, Save every flow: cycle1-bad-truncated.pcap -> 'The packet capture is incomplete: its last packet is cut off. Use a complete capture file.', 0 flows, nothing stored, page kept working. Empty and text files not re-run (refused without a crash at 06:08). | Pass | DEF-14 | test-results/ui_20261020/reg01/reg01_ui.json (pcap), pcap_cycle1-bad-truncated.png; evidence: product code = 940e082
2026-10-20 07:02 | TC-04 | SYS-02 | John Brian A. Tiopes | 0480899 | Synthetic PCAP, persistence All: all flows classified and saved. | Regression re-run after the PCAP change: cycle1-tc04-sample.pcap, Fast, Save every flow: 11 of 11 flows, 10 Attack / 1 Normal, 10 alerts, 11 queued, 11 synced, 0 pending, 0 not stored; 'The traffic source finished streaming.' | Pass |  | test-results/ui_20261020/reg01/reg01_ui.json (pcap), pcap_cycle1-tc04-sample.png; evidence: product code = 940e082
2026-10-20 07:02 | USE-01.3 | USE-01 | Brynt M. Timtiman | 0480899 | Error messages and status text are plain language (USE-01 card). | Fix build: Logs header 'Timestamp (UTC)', Alerts 'Detected (UTC)', Live Monitor 'Time (UTC)', Dashboard alert and log lines end in 'UTC' (7); 0 of 21 flow_accepted rows show 'None' (DEF-18 fixed); the 1e308 message is plain (TC-05 at 07:02). Still unlabelled UTC times: Dashboard 'Last at 2026-10-19 22:31:50' under Flows Analyzed, Nodes 'Requested'/'Decided', Accounts 'Created' and local-mode 'Deployed at' (DEF-16 not fully fixed; follow-up fix 128855e). | Fail | DEF-16 | test-results/ui_20261020/reg01/reg01_ui.json (labels), def09_dashboard_corrupt.png; evidence: product code = 940e082
2026-10-20 07:03 | REG-01.1 | REG-01 | Cel Hendrix N. San Miguel | 0480899 | Full automated suite re-run on the fix build; no new failures (REG-01 card; TC-14 second half). | Fix build 0480899 = 503cb9b + eight fix commits for DEF-01, 02, 03, 08, 09, 12, 13, 14, 16 and 18 (eecaac7..0480899). run_test_suites.py --all 06:58-07:03: pytest 550 passed / 67 deselected (13 more than on 503cb9b, the new tests for the fixes); pyright 0 errors; node 11 pass; integration 65 passed, 2 skipped (Npcap capture tests, terminal not elevated); pip-audit no known vulnerabilities; Bandit High 0 / Medium 14 / Low 18 (same as SEC-01.3). Ruff found 3 over-long lines, all in an uncommitted evidence script (test-results/ui_20261020/lighthouse/summarise_lighthouse.py), none in product code; after re-wrapping it (its output is unchanged) ruff check . passed. No new failures in product code. | Pass |  | test-results/suites_20261020_065849/summary.md and step logs; evidence: product code = 940e082
2026-10-20 07:03 | SEC-01.4 | SEC-01 | Arella Biacea B. Mirasol | 0480899 | No secrets in pages or API responses (SEC-01 card). | Signed-in analyst session, same-session requests to /, /monitor, /monitor/status, /simulation, /alerts, /logs, /reports, /nodes, /admins (redirects an analyst to the Dashboard) and /outbox/export: all HTTP 200, 0 matches for JWTs, Supabase keys, 'service_role', Bearer tokens, password/secret/key/token values, SUPABASE_/ALGOGUARD_ setting names and e-mail addresses (counts only were saved). No report existed to open, so report detail pages were not scanned. Repository and logs were checked in SEC-01 on 2026-10-19. Note: a UTC label edit to the Nodes page template was briefly on disk in the repository folder around 07:02-07:03 and then undone, so the Nodes header text may have come from it (label text only; no effect on this scan). | Pass |  | test-results/ui_20261020/reg01/reg01_ui.json (secrets); evidence: product code = 940e082
2026-10-20 07:05 | REG-01.2 | REG-01 | Cel Hendrix N. San Miguel | 0480899 | SMK-01 re-run on the fix build (REG-01 card). | TC-01 Normal row -> NORMAL 84.11%, deployment #1, synced as prediction #5011, no alert. TC-02 Attack row -> ATTACK 92.95%, synced as prediction #5012 with alert #4126. Replay algoguard_big, Fast, Save attacks, 07:03:24-07:05:24: 167 flows, 121 Attack / 46 Normal, 121 alerts, 121 queued, 121 synced, 0 pending, 0 not stored, no error. Outbox: all 2,099 events synced. | Pass |  | test-results/ui_20261020/reg01/reg01_ui.json (smoke), smk_*.png; evidence: product code = 940e082
2026-10-20 07:05 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 0480899 | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-13 (edf6193): 1e308 now refused in plain language at the form and /predict - closed. DEF-12 (edf6193): negative values now refused at the browser, the form and /predict, nothing stored; missing or empty numeric fields are still filled with training defaults and stored at the server (deliberate design, not changed) - TC-05 still fails on that part; DEF-12 stays open for a decision. DEF-14 (547044f): truncated capture refused, TC-04 sample unaffected - closed. DEF-18 (1ffa1b9): no 'None' messages - closed. DEF-16 (1ffa1b9): partly fixed; remaining labels in 128855e, re-tested on the final build. | Fail | DEF-12, DEF-13, DEF-14, DEF-16, DEF-18 | Test Log rows TC-05, SYS-02.1, TC-04, USE-01.3 at 07:02; test-results/ui_20261020/reg01/; evidence: product code = 940e082
2026-10-20 07:09 | REG-01.1 | REG-01 | Cel Hendrix N. San Miguel | 128855e | Full automated suite re-run on the final build; no new failures (REG-01 card). | Final build 128855e (0480899 + the remaining UTC labels for DEF-16): pytest 551 passed / 67 deselected; ruff all checks passed; pyright 0 errors; node 11 pass. Integration lane: see INT-01.2. | Pass |  | test-results/suites_final_128855e/*.log; evidence: product code = 940e082
2026-10-20 07:13 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 128855e | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-08 (2f4e087): the raw research/dataset/raw/UNSW_NB15_training-set.csv (45 columns incl. id and attack_cat) given to the training preparation on the final build -> 15 training columns, exactly the live flow features; id and attack_cat not used. Training itself was not re-run (no new model or run written). Not changed: local train.py --deploy still has no feature-schema check (local mode allows other schemas by design), so DEF-08 stays open for that part. | Pass | DEF-08 | test-results/ui_20261020/reg01/def08_schema_check.txt; tests/test_training_schema.py; evidence: product code = 940e082
2026-10-20 07:29 | ENV-02.1 | ENV-02 | Afel Anthonielle V. Quirao | ccbadd8 | GitHub Actions CI is green on the build commit (lint, type check, unit tests, browser polling tests) (ENV-02 card). | Run 39341292642 on ccbadd8 (product code 128855e plus test records), 07:23-07:29: setup-python 'python-version: 3.14.6' -> 'Successfully set up CPython (3.14.6)'; Lint 'All checks passed!'; Type check '0 errors, 26 warnings'; Unit tests '535 passed, 21 skipped, 34 deselected'; Browser polling tests 11 pass / 0 fail; conclusion success - the first green run on main since 2026-10-05. | Pass | DEF-01, DEF-03 | test-results/env_20261020/ci_run_39341292642_ccbadd8_success.log; https://github.com/AlgoGuard-CSThesis/AlgoGuard/actions/runs/39341292642; evidence: product code = 940e082
2026-10-20 07:29 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | ccbadd8 | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-01 and DEF-03 (f143b21): CI run 39341292642 installs the locked Python 3.14.6, and the model-loading tests and the outbox cap test pass on the runner; all four CI checks green (ENV-02.1 at 07:29) - both closed. DEF-02 (8b5133c): the README now tells testers to check 'Stopped services' after supabase start and restart the Edge Runtime; the integration lane passed with all services up (REG-01.1 at 07:03). The Supabase CLI behaviour itself is outside AlgoGuard - closed with the workaround documented. | Pass | DEF-01, DEF-02, DEF-03 | test-results/env_20261020/ci_run_39341292642_ccbadd8_success.log; README.md; evidence: product code = 940e082
2026-10-20 09:44 | USE-01.3 | USE-01 | Brynt M. Timtiman | 0480899 | Every shown time labelled UTC after the follow-up fix 128855e (DEF-16 re-test on the final build). | Planned on 128855e, but the app on port 5000 was still the process started at 07:00:28 on 0480899 (not restarted after main moved to 128855e), so the 128855e labels were not exercised. Seen on 0480899: Logs, Alerts, Live Monitor and Reports headers say UTC; 0 'None' messages; Dashboard 'Deployed at 2026-10-08 06:10:49 UTC'; still unlabelled: 'Last at 2026-10-19 23:05:24' and the Nodes 'Decided' header - as expected for 0480899. The 128855e labels are covered only by the automated tests that passed on 128855e (REG-01.1 at 07:09). | Fail | DEF-16 | test-results/ui_20261020/final/final_ui.json (labels; screenshots not captured - the browser window could not be drawn); evidence: product code = 940e082
2026-10-20 09:47 | REG-01.2 | REG-01 | Cel Hendrix N. San Miguel | 0480899 | SMK-01 re-run on the final build (REG-01 card). | Second smoke run, again on the 0480899 process (the app was not restarted on the final build 128855e, whose only product change is UTC label text in four templates). TC-01 -> NORMAL 84.11%, no alert; TC-02 -> ATTACK 92.95%, alert on upload; replay algoguard_big, Fast, Save attacks, 09:44:54-09:46:58: 191 flows, 138 Attack / 53 Normal, 138 alerts, 138 queued, 138 synced, 0 pending, 0 not stored, no error. | Pass |  | test-results/ui_20261020/final/final_ui.json (smoke), smk_replay.png (the TC-01/TC-02 screenshots were not captured); evidence: product code = 940e082
2026-10-20 10:02 | ENV-02.1 | ENV-02 | Afel Anthonielle V. Quirao | 33ca81d | GitHub Actions CI is green on the build commit (lint, type check, unit tests, browser polling tests) (ENV-02 card). | Run 39356261813 on 33ca81d (final product code 128855e plus test records and reports), 09:57-10:02: 'Successfully set up CPython (3.14.6)'; Lint 'All checks passed!'; Type check '0 errors, 26 warnings'; Unit tests '535 passed, 21 skipped, 34 deselected'; Browser polling tests 11 pass / 0 fail; conclusion success. | Pass |  | test-results/env_20261020/ci_run_39356261813_33ca81d_success.log; https://github.com/AlgoGuard-CSThesis/AlgoGuard/actions/runs/39356261813; evidence: product code = 940e082
2026-10-20 10:17 | REG-01.1 | REG-01 | Cel Hendrix N. San Miguel | 213d0be | Full automated suite re-run on the final build; no new failures (REG-01 card). | Final build 213d0be = 128855e + the DEF-12 fix (063f42f) and the DEF-08 fix (213d0be): pytest 566 passed / 67 deselected; ruff all checks passed; pyright 0 errors; node 11 pass; integration 65 passed, 2 skipped (Npcap capture tests, terminal not elevated). No new failures. | Pass |  | test-results/suites_20261020_101708/*.log; evidence: product code = 940e082
2026-10-20 10:17 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 213d0be | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-08 (2f4e087, 213d0be): the raw UNSW file trains on exactly the 15 flow features (07:13 check); any training file now loses id and attack_cat, also without the full flow schema and with a byte-order mark (test_id_and_attack_cat_are_never_features_even_without_the_full_flow_schema); train.py names missing and extra columns and says Live Monitor and publishing will refuse such a model (test_live_schema_note_*). Live Monitor already refuses incompatible models before capture. All passed in REG-01.1 at 10:17 - closed. | Pass | DEF-08 | test-results/suites_20261020_101708/pytest-offline.log; tests/test_training_schema.py; tests/test_cli_training.py; evidence: product code = 940e082
2026-10-20 10:20 | USE-01.3 | USE-01 | Brynt M. Timtiman | 213d0be | Error messages and status text are plain language; every shown time says it is UTC (USE-01 card; DEF-16 re-test on the final build). | App restarted at 10:19:41 on the final build 213d0be, analyst signed in. Dashboard 'Last at 2026-10-20 01:46:58 UTC' and 'Deployed at 2026-10-08 06:10:49 UTC' (no doubled 'UTC'), alert and log lines end in UTC (7); headers: Logs 'Timestamp (UTC)', Alerts 'Detected (UTC)', Live Monitor 'Time (UTC)', Reports 'Generated (UTC)', Nodes 'Decided (UTC)'; 0 'None' log messages. | Pass | DEF-16 | test-results/ui_20261020/final2/final2_ui.json (labels), dashboard_utc.png, nodes_utc.png; evidence: product code = 940e082
2026-10-20 10:20 | TC-05 | SYS-02 | John Brian A. Tiopes | 213d0be | Malformed input on Manual Prediction: missing field, text in a numeric field, an out-of-range number, a negative byte count - rejected with a plain message; nothing stored. | Final build: (a) dur emptied in the form with the browser check off -> 'Enter a value for every field; missing: dur.'; /predict with dur omitted, null or empty -> HTTP 400 with the same message. Flows Analyzed 2,551 before and after: nothing stored. (b) 'abc' is blocked by the browser number field (06:08) and refused by the server ('must contain a finite numerical value', unit tests); (c) 1e308 and (d) negative values refused in plain language (07:02, unchanged code). All four inputs are now refused and nothing is stored. | Pass | DEF-12 | test-results/ui_20261020/final2/final2_ui.json (def12), def12_form_empty_dur.png; evidence: product code = 940e082
2026-10-20 10:23 | ENV-02.1 | ENV-02 | Afel Anthonielle V. Quirao | 213d0be | GitHub Actions CI is green on the build commit (lint, type check, unit tests, browser polling tests) (ENV-02 card). | Run 39358135540 on the final build 213d0be, finished 10:22:59: 'Successfully set up CPython (3.14.6)'; Lint 'All checks passed!'; Type check '0 errors, 26 warnings'; Unit tests '550 passed, 21 skipped, 34 deselected'; Browser polling tests 11 pass / 0 fail; conclusion success. | Pass |  | test-results/env_20261020/ci_run_39358135540_213d0be_success.log; https://github.com/AlgoGuard-CSThesis/AlgoGuard/actions/runs/39358135540; evidence: product code = 940e082
2026-10-20 10:23 | REG-01.2 | REG-01 | Cel Hendrix N. San Miguel | 213d0be | SMK-01 re-run on the final build (REG-01 card). | Final build 213d0be: TC-01 Normal row -> NORMAL 84.11%, deployment #1, synced as prediction #5274, no alert. TC-02 Attack row -> ATTACK 92.95%, synced as prediction #5275 with alert #4387. Replay algoguard_big, Fast, Save attacks, 10:21:22-10:23:22: 169 flows, 123 Attack / 46 Normal, 123 alerts, 123 queued, 123 synced, 0 pending, 0 not stored, no error. Outbox: all 2,364 events synced. | Pass |  | test-results/ui_20261020/final2/final2_ui.json (smoke), smk_*.png; evidence: product code = 940e082
2026-10-20 10:23 | TC-14 | REG-01 | Cel Hendrix N. San Miguel | 213d0be | DEF card marked fixed with its commit: failing case re-run on the fix commit: case passes; no new failures. | DEF-12 (edf6193, 063f42f): TC-05 passes on the final build - omitted, null and empty fields refused at the form and /predict, nothing stored - closed. DEF-16 (1ffa1b9, 128855e): every shown time says UTC on the final build (USE-01.3 at 10:20) - closed. Every fixed DEF card is now re-tested and closed; open: the cycle 2 items DEF-04..07, 10, 11, 17. | Pass | DEF-12, DEF-16 | Test Log rows TC-05, USE-01.3 and REG-01.2 at 10:20-10:23; test-results/ui_20261020/final2/; evidence: product code = 940e082

## Defects
Defect ID | Date found | Case / Card | Card owner | Title | Severity | Priority | Steps to reproduce | Expected | Actual | Build | Environment | Status | Fixed in commit | Re-test result
DEF-01 | 2026-10-19 | ENV-02.1 / ENV-02 | Afel Anthonielle V. Quirao | CI installs Python 3.14.8 instead of the locked 3.14.6, so every model-loading unit test stops with ModelDeliveryError and CI is red on main | Medium | High | 1. Open GitHub > AlgoGuard-CSThesis/AlgoGuard > Actions > CI. 2. Open run 38886300881 (cb3bcdb) or 38870178965 (940e082), job 'checks'. 3. In 'Run actions/setup-python@v5' see 'python-version: 3.14' and 'Successfully set up CPython (3.14.8)'. 4. In 'Unit tests' see 40 errors and 4 failures with model_runtime.ModelDeliveryError. | CI runs on the locked runtime (requirements-model.lock / model_runtime.PYTHON_VERSION = 3.14.6, as the workflow comment itself says) and all steps are green. | Unit tests: '5 failed, 476 passed, 21 skipped, 34 deselected, 40 errors'; 44 of the 45 are ModelDeliveryError ('Install the locked Python model runtime.' x43 from model_runtime.py:38; 'Retrain this artifact with the locked model runtime.' x1 from model_runtime.py:74), because .github/workflows/ci.yml asks setup-python for '3.14' and gets 3.14.8. The remaining failure is DEF-03. Browser polling tests are then skipped. All six main runs since 2026-10-05 failed. The app's refusal of an unlocked runtime is by design; the defect is the unpinned CI Python version. Not reproduced on PC A: the working copy passes (537 passed), and so does a clean clone of cb3bcdb with a fresh Python 3.14.6 venv from requirements-dev.txt only (521 passed, 21 skipped, 34 deselected; exit 0; the 21 skips are 16 tests in test_maintainer_env.py and 5 integration modules that need psycopg2 from requirements-maintainer.txt, which CI does not install either), because PC A runs the locked 3.14.6. | cb3bcdb (CI); 940e082 (CI) | GitHub Actions windows-latest; setup-python '3.14' (patch level not pinned; requirements-model.lock records 3.14.6); Node 22 | Closed | f143b21 | 2026-10-20 07:29 ENV-02.1 Pass: CI run 39341292642 sets up CPython 3.14.6; unit tests 535 passed, 21 skipped; all four checks green.
DEF-02 | 2026-10-19 | ENV-02.2 / ENV-02 | Afel Anthonielle V. Quirao | Local stack: supabase start exits 0 but leaves the crashed Edge Runtime stopped; Edge Function integration tests then fail with HTTP 503 | Low | Medium | 1. Let the supabase_edge_runtime_AlgoGuard container stop (here it had exited with code 255 eleven days earlier). 2. Run npx supabase start (CLI 2.117.0); it exits 0 and lists the Edge Runtime under 'Stopped services'. 3. Run python -m pytest -q -m integration. | supabase start brings up every service enabled in supabase/config.toml ([edge_runtime] enabled = true), or fails; the integration lane passes. | Exit 0 with the Edge Runtime still stopped; 5 integration tests fail with HTTP 503 'name resolution failed' from /functions/v1/account_admin. Workaround: docker start supabase_edge_runtime_AlgoGuard, then the lane passes (65 passed, 2 skipped). The same stopped Edge Runtime was noted in 05f-pilot.md section 8.2 (2026-09-30). Test-environment issue; the product is not affected. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; Docker Desktop 29.8.0; Supabase CLI 2.117.0 local stack | Closed | 8b5133c (README workaround) | 2026-10-20 07:03 integration lane 65 passed, 2 skipped with all services up. The Supabase CLI still exits 0 with a stopped container (outside AlgoGuard); the README step is the documented workaround.
DEF-03 | 2026-10-19 | ENV-02.1 / ENV-02 | Afel Anthonielle V. Quirao | test_cap_reserves_before_enqueue_and_retry_does_not_consume_slot fails on the CI runner: 300 queued outbox writes do not finish within drain()'s 5 s limit | Low | Medium | 1. Open CI run 38886300881 (cb3bcdb) or 38870178965 (940e082), job 'checks', step 'Unit tests'. 2. Find tests/test_cloud_outbox.py::test_cap_reserves_before_enqueue_and_retry_does_not_consume_slot. | spool.drain() returns True after 300 events are queued (test line 55). | 'assert spool.drain()' -> False in both runs. Outbox.drain() waits at most 5 s (cloud_outbox.py:554-558) for the writer thread to persist the queue. Passes on PC A in the working copy and in the clean clone. The model runtime is not involved. Most likely the GitHub windows-latest runner writes the 300 SQLite rows more slowly than 5 s; not confirmed. It would keep CI red after DEF-01 is fixed. | cb3bcdb (CI); 940e082 (CI) | GitHub Actions windows-latest; CPython 3.14.8 | Closed | f143b21 | 2026-10-20 07:29 ENV-02.1 Pass: the outbox cap test passes on the CI runner (run 39341292642).
DEF-04 | 2026-10-19 | TC-03 / SYS-01 | Victor Alexander A. Ong | Deployed model misses the accuracy target on the independent evaluation set (81.47% vs >= 90%) | High | High | 1. On the build commit, with the venv active, run: python scripts/evaluate_model.py --model saved_models/run_3/stacking.joblib --compare-dir saved_models/run_3 2. The script removes every UNSW_NB15_training-set.csv row whose 15 features appear in datasets/*.csv and scores the rest (53,243 rows). 3. Read 'accuracy' in summary.md. | accuracy >= 90% (Master Test Plan 3.3). | accuracy = 81.47% on 53,243 unseen rows (20,674 attack / 32,569 normal). Full result: accuracy 81.47%, F1 79.49%, recall 92.44%, FPR 25.49%, ROC-AUC 0.9371; FP 8,301 of 32,569 normal flows. The same model scores accuracy 96.98% / F1 97.77% / FPR 4.07% on algoguard_big.csv, the data it was trained on: a generalisation gap from training on a 5,000-row sample. | dafe5e5 (product code = 940e082); model SHA-256 9c9f0fb1...847c (deployment #1) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; scikit-learn 1.9.0 | Open
DEF-05 | 2026-10-19 | TC-03 / SYS-01 | Victor Alexander A. Ong | Deployed model misses the F1-score target on the independent evaluation set (79.49% vs >= 90%) | High | High | 1. On the build commit, with the venv active, run: python scripts/evaluate_model.py --model saved_models/run_3/stacking.joblib --compare-dir saved_models/run_3 2. The script removes every UNSW_NB15_training-set.csv row whose 15 features appear in datasets/*.csv and scores the rest (53,243 rows). 3. Read 'F1-score' in summary.md. | F1-score >= 90% (Master Test Plan 3.3). | F1-score = 79.49% on 53,243 unseen rows (20,674 attack / 32,569 normal). Full result: accuracy 81.47%, F1 79.49%, recall 92.44%, FPR 25.49%, ROC-AUC 0.9371; FP 8,301 of 32,569 normal flows. The same model scores accuracy 96.98% / F1 97.77% / FPR 4.07% on algoguard_big.csv, the data it was trained on: a generalisation gap from training on a 5,000-row sample. | dafe5e5 (product code = 940e082); model SHA-256 9c9f0fb1...847c (deployment #1) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; scikit-learn 1.9.0 | Open
DEF-06 | 2026-10-19 | TC-03 / SYS-01 | Victor Alexander A. Ong | Deployed model misses the false-positive rate target on the independent evaluation set (25.49% vs <= 8%) | High | High | 1. On the build commit, with the venv active, run: python scripts/evaluate_model.py --model saved_models/run_3/stacking.joblib --compare-dir saved_models/run_3 2. The script removes every UNSW_NB15_training-set.csv row whose 15 features appear in datasets/*.csv and scores the rest (53,243 rows). 3. Read 'false-positive rate' in summary.md. | false-positive rate <= 8% (Master Test Plan 3.3). | false-positive rate = 25.49% on 53,243 unseen rows (20,674 attack / 32,569 normal). Full result: accuracy 81.47%, F1 79.49%, recall 92.44%, FPR 25.49%, ROC-AUC 0.9371; FP 8,301 of 32,569 normal flows. The same model scores accuracy 96.98% / F1 97.77% / FPR 4.07% on algoguard_big.csv, the data it was trained on: a generalisation gap from training on a 5,000-row sample. | dafe5e5 (product code = 940e082); model SHA-256 9c9f0fb1...847c (deployment #1) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; scikit-learn 1.9.0 | Open
DEF-07 | 2026-10-19 | TC-03 / SYS-01 | Victor Alexander A. Ong | Deployed model misses the ROC-AUC target on the independent evaluation set (0.9371 vs >= 0.95) | High | High | 1. On the build commit, with the venv active, run: python scripts/evaluate_model.py --model saved_models/run_3/stacking.joblib --compare-dir saved_models/run_3 2. The script removes every UNSW_NB15_training-set.csv row whose 15 features appear in datasets/*.csv and scores the rest (53,243 rows). 3. Read 'ROC-AUC' in summary.md. | ROC-AUC >= 0.95 (Master Test Plan 3.3). | ROC-AUC = 0.9371 on 53,243 unseen rows (20,674 attack / 32,569 normal). Full result: accuracy 81.47%, F1 79.49%, recall 92.44%, FPR 25.49%, ROC-AUC 0.9371; FP 8,301 of 32,569 normal flows. The same model scores accuracy 96.98% / F1 97.77% / FPR 4.07% on algoguard_big.csv, the data it was trained on: a generalisation gap from training on a 5,000-row sample. | dafe5e5 (product code = 940e082); model SHA-256 9c9f0fb1...847c (deployment #1) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; scikit-learn 1.9.0 | Open
DEF-08 | 2026-10-19 | SYS-01.5 / SYS-01 | Victor Alexander A. Ong | train.py uses every non-target column as a feature: on the raw UNSW-NB15 file it trains on attack_cat (the label) and id, reports 100%, and local --deploy has no feature-schema check | Medium | High | 1. Build a CSV with the UNSW_NB15_training-set.csv columns (e.g. the training file itself, or test-results/sys01_holdout/make_holdout.py's model_b_train.csv). 2. python train.py <that CSV> --models-dir saved_models/cycle1_B (no --deploy). 3. Read the comparison table and the artifact's feature_columns. | Training uses only the supported 15-feature flow schema (model_runtime FEATURE_SCHEMA_VERSION 'unsw-nb15-fifteen-v1'), or refuses a CSV with other columns; label-derived columns such as attack_cat are never features. | preprocessing_service.prepare_dataset() takes every column except the last as a feature: 44 features including attack_cat and id. Random Forest, AdaBoost, Gradient Boosting, Naive Bayes and Stacking report 100.00% accuracy / F1 / ROC-AUC (Naive Bayes is 48.72% on 15 features). Cloud publication and download refuse such a model (model_runtime.verify_artifact_contract, called from publish_model.py and model_delivery.py), but the local deploy path (train.py _deploy_stacking -> deployment_service.deploy_model) does not call it - by code reading; --deploy was not run. Workaround: train only on CSVs with the 15 features + label, as the bundled datasets are. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; local training run 5 | Closed | 2f4e087, 213d0be | 2026-10-20 07:13 TC-14 Pass: the raw UNSW-NB15 training file gives exactly the 15 flow features. 10:17 TC-14 Pass on 213d0be: id and attack_cat are dropped from any training file, and train.py warns before training and before --deploy when a model cannot run on captured traffic (Lead Architect decision: warn, not refuse).
DEF-09 | 2026-10-19 | TC-08 / INT-01 | Afel Anthonielle V. Quirao | Dashboard shows the model as 'Deployed' while this installation's cached model is corrupt and refused | Low | Low | 1. Stop the app (cloud mode); back up the model cache folder. 2. Change one byte in the cached .joblib under <state dir>\models. 3. Start the app and sign in as an analyst. 4. Open the Dashboard, then Predict. | Every page that reports model status says the model cannot be used on this PC (as Predict does). | Predict: 'No active deployment - The cached model is corrupt. Remove it and retry.' Dashboard: green 'Deployed' badge, Stacking Ensemble, deployment #1 and its training metrics, with no warning. cloud_app.py dashboard() renders active_deployment(repo), the cloud record, and does not check the local cache (the model_message path only covers errors from that cloud lookup). No unsafe behaviour: the corrupt model is never used. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; cloud mode, PC A analyst | Closed | eecaac7, 0480899 | 2026-10-20 07:01 TC-14 Pass: with a corrupted cached copy the Dashboard shows 'Unavailable here' and the reason; after restoring the backup it shows 'Deployed' again.
DEF-10 | 2026-10-19 | PRF-01.P1 / PRF-01 | Afel Anthonielle V. Quirao | Pilot limit L2: p95 upload acknowledgement 24.06 s on one live capture (budget <= 5 s) | Medium | Medium | From the pilot record (not re-run in cycle 1): 1. PC B, live capture 6 on 2026-10-10 (Default interface, save attacks, commit 4c9666c). 2. Measure upload delay as cloud received_at minus client event_time for the stored events. | p95 upload acknowledgement <= 5 s (pilot acceptance target, 2026-10-08). | 'p95 24.06 s, max 36.65 s, with 25 events taking 20-30 s+ around 01:12:25-01:12:44Z.' Not reproduced on 2026-10-16 (capture 19 p95 3.44 s, newer code 940e082); the other 11 runs met the budget. 'Cause not identified.' The pilot recorded it as limit L2 rather than re-targeting it. | 4c9666c (PC B, 2026-10-10) | PC B (LAPTOP-PNL5IIAJ), Wi-Fi, hosted Supabase pilot (Tokyo) | Open
DEF-11 | 2026-10-19 | PRF-01.P2 / PRF-01 | Afel Anthonielle V. Quirao | Pilot limit L1: sustained >= 20 acknowledged events/s per client not demonstrated; shipped sources are paced below it | Medium | Medium | From the pilot record (not re-run in cycle 1): 1. Run a CSV replay at Fast speed and count acknowledged events per second. 2. Note the replay pace (SPEED_CHOICES: Fast = one flow per 0.35 s) and the 300-event storage cap per capture. | Sustained acknowledged events per client >= 20 events/s (pilot budget; also Master Test Plan 3.4). | PC A '≈ 1.9/s (capture 5: 300 events in 157 s)'; PC B 'backlog drain of 210 events in 4.1 s ≈ 51/s'. 'Sources are paced by design: CSV Fast emits one flow per 0.35 s, ≤ 2.9/s. Each capture stores at most 300 events.' 'A sustained-load harness is needed.' Recorded by the pilot as limit L1. | pilot 4c9666c / 9e18f30 | PC A and PC B, hosted Supabase pilot (Tokyo) | Open
DEF-12 | 2026-10-20 | TC-05 / SYS-02 | John Brian A. Tiopes | Manual Prediction and /predict accept missing, empty and negative numeric input: missing values are filled with training defaults and the record is saved | Medium | High | 1. Signed in, POST /predict (JSON) with the TC-01 Normal row but without 'dur', or with 'dur': ''. 2. Repeat with 'sbytes': '-5'. (Equivalent: call services.simulation_service.predict_with_artifact with model A, test-results/sys02_files/tc05_server_validation.py.) | Missing or empty fields and negative byte or packet counts are rejected with a plain message; nothing is classified or stored (TC-05). | Missing dur -> accepted, filled from the artifact's feature_defaults (simulation_service.py:94), Normal 56.67%; empty dur -> accepted (NaN imputed), 56.67%; sbytes -5 -> accepted, Normal 86.65%. Accepted input is queued for upload (cloud_app.py:415-418). The cloud Manual Prediction form also fills absent fields with defaults before validating (cloud_app.py:608-611). The browser form blocks empty fields (required) but has no min/max, so negatives pass. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; model A (deployment #1) | Closed | edf6193, 063f42f | 2026-10-20 07:02: negative values refused, nothing stored. 10:20 TC-05 Pass on 213d0be (Lead Architect decision: refuse missing fields): omitted, null and empty fields refused at the form and /predict with 'Enter a value for every field; missing: dur.', nothing stored.
DEF-13 | 2026-10-20 | TC-05 / SYS-02 | John Brian A. Tiopes | An out-of-range number (1e308) is refused with a technical scikit-learn message, not plain language | Low | Low | POST /predict or Manual Prediction with the TC-01 row and sbytes = 1e308. | A plain message such as 'sbytes is out of range'. | 'Prediction failed: Input X contains infinity or a value too large for dtype('float32').' The value passes the finite-number check (simulation_service.py:99-108) and fails inside the model. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; model A | Closed | edf6193 | 2026-10-20 07:02 TC-05 re-run Pass: 1e308 -> 'sbytes is too large to classify; enter a smaller value.' at the form and /predict; nothing stored.
DEF-14 | 2026-10-20 | SYS-02.1 / SYS-02 | John Brian A. Tiopes | A truncated PCAP is replayed partially without telling the user it is cut short | Low | Medium | 1. Use captures/cycle1-bad-truncated.pcap (first 60% of the TC-04 sample). 2. Replay it (Live Monitor > Recorded packets, or PcapReplaySource directly). | The file is rejected, or the user is told the capture is truncated (SYS-02 card: bad files rejected without a crash). | Not refused: 49 packets read, 7 flows classified; the only sign is a scapy console warning 'Pcap: packet has been truncated'. No crash. Empty and text files are refused correctly. | dafe5e5 (product code = 940e082) | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv | Closed | 547044f | 2026-10-20 07:02 SYS-02.1 re-run Pass: 'The packet capture is incomplete: its last packet is cut off. Use a complete capture file.', 0 flows; TC-04 sample still 11 of 11 flows.
DEF-15 | 2026-10-19 | TC-12 / USE-01 | Brynt M. Timtiman | Live Monitor's scrolling flow feed cannot be reached by keyboard (Lighthouse: scrollable content not keyboard-accessible) | Medium | Medium | 1. Sign in and open Live Monitor. 2. Run Chrome Lighthouse > Accessibility, or press Tab through the page. | Every scrollable region can be focused and scrolled with the keyboard. | Reported through the fix commit 503cb9b ('fix the Ensure elements that have scrollable content are accessible by keyboard in Safari', 2026-10-19 19:48, from the USE-01 owner's account): the .monitor-feed-scroll container had no tabindex, role or label. The Lighthouse report itself was not received by the log keeper. | 940e082 (found); fixed in 503cb9b | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; Chrome Lighthouse | Closed | 503cb9b | 2026-10-20 06:24 TC-14 Pass: feed reached with Tab, PageDown scrolls it, focus outline visible; Lighthouse 12.6 Accessibility 100 on Live Monitor; full suite passed on 503cb9b.
DEF-16 | 2026-10-20 | USE-01.3 / USE-01 | Brynt M. Timtiman | Feed, alert and log times are shown in UTC without saying so | Low | Medium | 1. On PC A (UTC+8), run a replay at a known local time. 2. Read the Recent Flows TIME column, the Dashboard alerts and System Logs. | Times in local time, or clearly labelled UTC as 'Deployed at' and Reports ('Generated (UTC)') already are. | Recent Flows shows 22:15:45 for a flow at 06:15:45 local; System Logs' newest line reads 2026-10-19 22:15:46 for 2026-10-20 06:15:46 local - even the date looks a day behind. Seen in SMK-01, TC-09 and USE-01. | 503cb9b | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; cloud mode | Closed | 1ffa1b9, 128855e | 2026-10-20 07:02 on 0480899: partly fixed (Dashboard 'Last at', Nodes, Accounts and local 'Deployed at' still unlabelled; fixed in 128855e). 10:20 USE-01.3 Pass on the final build 213d0be: every shown time says UTC.
DEF-17 | 2026-10-20 | TC-11 / PRF-01 | Afel Anthonielle V. Quirao | Live event-to-verdict lag p95 is 895.6 ms for flows ended by FIN/RST (budget <= 500 ms) | Medium | Medium | 1. Start the app as administrator; Live Monitor > Live interface capture, Save attacks. 2. Browse normally for 90 s. 3. Read detection_lag_ms and end_reason per flow from /monitor/status; take flows with end_reason fin or rst. | p95 <= 500 ms (Master Test Plan 3.4). | n=32 FIN/RST flows: p50 388.9 ms, p95 895.6 ms. Model latency alone p50 163.9 ms, p95 377.2 ms, so roughly half the delay is queueing and handling around the model. Measured with a traffic generator and Chrome running on PC A; the app also stores no per-flow lag, so this can only be measured live. | 503cb9b | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; Intel Wi-Fi 6 AX203, Npcap 1.88, administrator | Open
DEF-18 | 2026-10-20 | USE-01.3 / USE-01 | Brynt M. Timtiman | System Logs show the word 'None' as the message of every flow_accepted entry | Low | Low | Run any replay in cloud mode, then open Logs. | An empty message cell or a readable message. | Each 'detection / flow_accepted / success' row has the message 'None' (a Python null rendered as text). | 503cb9b | PC A (SANMIGUEL), Windows 11 Home 26H2 build 26300.9711, Python 3.14.6 venv; cloud mode | Closed | 1ffa1b9 | 2026-10-20 07:02 USE-01.3 re-run: 0 of 21 flow_accepted rows show 'None' - Pass.

## Automated Runs
Date / time | Step | Build | Result | Key line | Log file
2026-10-19 10:51 | TC-16 coverage: python -m pytest --cov=services --cov-report=term -q | dafe5e5 | PASS | 537 passed, 67 deselected, 18 warnings in 290.45s; TOTAL 1869 stmts, 312 miss, 83% | test-results/coverage_20261019_104655/pytest-cov.log
2026-10-19 13:13 | DEF-01 reproduction: clean clone of cb3bcdb, fresh venv (Python 3.14.6, requirements-dev.txt only, no .env, no saved models), python -m pytest -q | cb3bcdb | PASS | 521 passed, 21 skipped, 34 deselected in 406.65s (0:06:46); pytest exit 0 | test-results/env_20261019/ci-repro.log; test-results/env_20261019/ci-repro-pytest.log
2026-10-19 13:18 | DEF-01 reproduction re-run with skip reasons: same clean clone, python -m pytest -q -rs | cb3bcdb | PASS | 521 passed, 21 skipped, 34 deselected in 157.92s; every skip = psycopg2 missing (requirements-maintainer.txt): 16 in test_maintainer_env.py, 5 integration modules | test-results/env_20261019/ci-repro-pytest-rs.log
2026-10-19 13:26 | pytest-offline: python -m pytest -q | dafe5e5 | PASS | 537 passed, 67 deselected in 130.13s (0:02:10) | test-results/suites_20261019_132412/pytest-offline.log
2026-10-19 13:26 | ruff-lint: python -m ruff check . | dafe5e5 | PASS | All checks passed! | test-results/suites_20261019_132412/ruff-lint.log
2026-10-19 13:26 | pyright-typecheck: npm run typecheck | dafe5e5 | PASS | 0 errors, 0 warnings, 0 informations | test-results/suites_20261019_132412/pyright-typecheck.log
2026-10-19 13:26 | node-monitor-poll: node --test tests/monitor_poll.test.cjs | dafe5e5 | PASS | # pass 11 / # fail 0 | test-results/suites_20261019_132412/node-monitor-poll.log
2026-10-19 13:27 | pytest-integration: python -m pytest -q -m integration | dafe5e5 | FAIL | 5 failed, 60 passed, 2 skipped, 537 deselected in 54.27s; all 5 = Edge Function HTTP 503 (Edge Runtime container stopped, DEF-02) | test-results/suites_20261019_132412/pytest-integration.log
2026-10-19 13:28 | pip-audit: python -m pip_audit -r requirements.txt | dafe5e5 | PASS | No known vulnerabilities found | test-results/suites_20261019_132412/pip-audit.log
2026-10-19 13:28 | bandit: python -m bandit -r <top-level *.py> services scripts | dafe5e5 | FAIL | Exit 1 (issues found). By severity: High 0, Medium 14, Low 18. (The runner's summary line shows the by-confidence counts by mistake: Medium 16 / High 16.) | test-results/suites_20261019_132412/bandit.log
2026-10-20 04:59 | REG-01 pytest-offline: python -m pytest -q | 503cb9b | PASS | 537 passed, 67 deselected in 139.19s (0:02:19) | test-results/suites_20261020_045724/pytest-offline.log
2026-10-20 04:59 | REG-01 ruff-lint: python -m ruff check . | 503cb9b | PASS | All checks passed! | test-results/suites_20261020_045724/ruff-lint.log
2026-10-20 05:00 | REG-01 pyright-typecheck: npm run typecheck | 503cb9b | PASS | 0 errors, 0 warnings, 0 informations | test-results/suites_20261020_045724/pyright-typecheck.log
2026-10-20 05:00 | REG-01 node-monitor-poll: node --test tests/monitor_poll.test.cjs | 503cb9b | PASS | # pass 11 / # fail 0 | test-results/suites_20261020_045724/node-monitor-poll.log
2026-10-20 05:00 | REG-01 pytest-integration: python -m pytest -q -m integration | 503cb9b | PASS | 65 passed, 2 skipped, 537 deselected in 49.47s | test-results/suites_20261020_045724/pytest-integration.log
2026-10-20 05:01 | REG-01 pip-audit: python -m pip_audit -r requirements.txt | 503cb9b | PASS | No known vulnerabilities found | test-results/suites_20261020_045724/pip-audit.log
2026-10-20 05:01 | REG-01 bandit | 503cb9b | FAIL | Exit 1 (issues found). By severity: High 0, Medium 14, Low 18 - unchanged, all Medium justified in SEC-01.3. (Runner summary shows the by-confidence counts.) | test-results/suites_20261020_045724/bandit.log
2026-10-19 13:30 | pytest-integration re-run after docker start supabase_edge_runtime_AlgoGuard: python -m pytest -q -m integration -rfEs | dafe5e5 | PASS | 65 passed, 2 skipped, 537 deselected in 43.70s; skips = 2 Npcap capture tests (RUN_WINDOWS_CAPTURE_TESTS not set) | test-results/integration_20261019_132933/pytest-integration.log

## Exit Criteria
Criterion | Target | Measured | Met / Not met / Not measured | Source
3.3 · 100% of planned Critical test cases executed | 100% | 6 of 7 (86%): TC-01, TC-02, TC-03, TC-04, TC-08, TC-09 executed; TC-06 not executed (second PC unavailable - pilot evidence and the automated two-node test only). Counted by card priority instead (Critical cards SMK-01, SYS-01, SYS-03, UAT-01: TC-01, TC-02, TC-03, TC-06, TC-07, TC-15): 3 of 6. | Not met | Critical = test cases traced to Critical features F2, F7, F8 in the RTM: TC-01, TC-02, TC-03, TC-04, TC-06, TC-08, TC-09; Test Log
3.3 · Overall pass rate across executed test cases | >= 95% | 84.6% of executed test cases (11 of 13: TC-01, TC-02, TC-04, TC-05, TC-08, TC-09, TC-10, TC-12, TC-13, TC-14, TC-16 passed on their latest run; TC-03 and TC-11 failed; TC-06, TC-07, TC-15 not executed). 78.7% of executed Test Log rows (74 Pass of 94, earlier failed runs included). | Not met | Test Log
3.3 · Open Critical or High severity bugs | 0 | 4 High open (DEF-04, DEF-05, DEF-06, DEF-07); 0 Critical | Not met | Defects sheet
3.3 · Accuracy on the independent evaluation set | >= 90% | 81.47% (53,243 rows; model A, deployment #1) | Not met | TC-03 · test-results/evaluation_20261019_153649 · DEF-04
3.3 · F1-score on the independent evaluation set | >= 90% | 79.49% | Not met | TC-03 · test-results/evaluation_20261019_153649 · DEF-05
3.3 · Attack recall on the independent evaluation set | >= 90% | 92.44% | Met | TC-03 · test-results/evaluation_20261019_153649
3.3 · False-positive rate on the independent evaluation set | <= 8% | 25.49% | Not met | TC-03 · test-results/evaluation_20261019_153649 · DEF-06
3.3 · ROC-AUC on the independent evaluation set | >= 0.95 | 0.9371 | Not met | TC-03 · test-results/evaluation_20261019_153649 · DEF-07
3.3 · Every performance budget in 3.4 met or waived in writing by the Product Owner | All met or waived | Lag p95 not met (895.6 ms, DEF-17) and events per second not met (1.65-1.92/s, DEF-11); packet drop, soak CPU and soak RAM met; no written waiver | Not met | 3.4 rows below
3.3 · Open Low/Medium defects have documented workarounds and Product Owner sign-off | All | 3 Medium defects open (DEF-10, 11, 17 - throughput and lag limits, for cycle 2), without written workarounds; 11 Low/Medium defects (DEF-01, 02, 03, 08, 09, 12, 13, 14, 15, 16, 18) fixed, re-tested and closed. No Product Owner sign-off yet | Not met | Defects sheet; docs/testing/cycle-1/defects.md
3.3 · Final Test Completion Report generated and accepted (DOC-06) | Generated and accepted | Generated 2026-10-20 (v1.0); not yet accepted - approval signatures blank | Not met | docs/testing/cycle-1/3 - AlgoGuard Test Completion Report v1.0.docx
3.4 · Live event-to-verdict lag, p95 (excluding flow timeouts) | <= 500 ms | 895.6 ms p95 (p50 388.9 ms) over 32 flows ended by FIN/RST in a 90 s live capture of ordinary browsing on PC A | Not met | TC-11 · test-results/ui_20261020/tc11_live.json · DEF-17
3.4 · Sustained events per second, per client | >= 20 | 1.65 flows/s over the 30-minute Fast replay; 1.92 events/s (TC-09 replay, 202 events in 105 s); paced source, max 2.86/s | Not met | PRF-01.5, PRF-01.1 · DEF-11
3.4 · Packet drop fraction during live capture | <= 1% | 0% (0 of 8,721 packets in the 90 s live capture) | Met | PRF-01.3 · test-results/ui_20261020/tc11_live.json
3.4 · AlgoGuard process CPU during a 30-minute soak | <= 80% | Max 8.03%, mean 7.54% of the machine (60 samples, 06:28-06:57) | Met | PRF-01.4 · test-results/soak_20261020_062732.csv
3.4 · AlgoGuard process RAM during a 30-minute soak | <= 1 GiB | Max 352.2 MB; 322.0 MB at the end; whole-run trend -0.1 MB/min (a climb of about 29 MB from 06:32 to 06:52 then flat - a longer soak is suggested) | Met | PRF-01.4 · test-results/soak_20261020_062732.csv

## By Owner
Owner | Cards | Cases executed | Passed | Failed | Not executed | Defects raised
Jan Leigh Augustine A. Munoz | DOC-01, LOG-01 | 0 | 0 | 0 | 0 | 0
Chate Mae N. Caluba | DOC-02, DOC-06 | 0 | 0 | 0 | 0 | 0
Victor Alexander A. Ong | DOC-03, SYS-01 | 6 | 4 | 2 | 0 | 5
John Brian A. Tiopes | DOC-04, SMK-01, SYS-02 | 15 | 10 | 5 | 2 | 3
Brynt M. Timtiman | DOC-05, USE-01 | 7 | 4 | 3 | 1 | 3
Arella Biacea B. Mirasol | ENV-01, SEC-01 | 18 | 18 | 0 | 1 | 0
Afel Anthonielle V. Quirao | ENV-02, INT-01, PRF-01 | 28 | 19 | 9 | 3 | 7
Cel Hendrix N. San Miguel | UNT-01, SYS-03, REG-01 | 20 | 19 | 1 | 4 | 0
Pauleen Joy O. Gomez | UAT-01 | 0 | 0 | 0 | 1 | 0
Counts are Test Log rows (one per execution, re-runs included). Cases executed = Pass + Fail. Blocked rows are counted under Not executed. Defects are counted against the owner of the card that found them.